## My VA
My VA
Sprints | Payment info updates | Medical copays
Sprint 58 (10/6 - 10/19) | Meet with edu team | N/A
Sprint 59 (10/20 - 11/2) | Scope project PM: Schedule discussion on discovery findings for end of sprint Design: Discovery -- determine the direction of work | N/A
Sprint 60 (11/3- 11/16) | Determine next steps PM: Nothing Design: Present findings; work with team to determine next steps; FE: Technical discovery, if needed | N/A
Sprint 61 (11/17 - 11/30) | Project pivot to payment information PM: Collab kickoff Design: Additional payment info discovery; Meet with debt team to understand feature; preliminary designs; Define scope FE: Do we need any technical discovery now? I don't think so. | N/A
Sprint 62 (12/1 - 12/14) | Design intent - Design; Design intent - Technical discovery | N/A
Sprint 63 (12/15 - 12/28) | Research/midpoint review planning - Midpoint review planning, including starting to put together list of test cases - Finish design if not already done - Technical discovery | N/A
Sprint 64 (12/29 - 1/11) | Midpoint review; Research planning - Hold midpoint review - Research planning/convo guide/ recruit; If not done, finish design on how to handle "benefits you might be interested in"; if done, create FE tickets - Prototype build on payment info | N/A
Sprint 65 (1/12 - 1/25) | Continue build - Conduct and summarize research - Update documentation if time - Updates from user research (may go into the following sprint depending on updates) - Determine what, if anything, still needs to happen with FE build, and complete build | N/A
Sprint 66 (1/26 - 2/8) | Finish build - PM: Do we need UAT? - Design for any updates coming out of testing; Onboard Angela - Request QA depending where build is at -- Are we ready for QA? - Update documentation if needed - Finish build | N/A
Sprint 67 (2/9 - 2/22) | Liz to transition My VA work over to Angela; All final updates ahead of QA - PM: Review QA test cases and make sure they are accurate given any updates from user testing - Team does informal click through of the feature to make sure it is ready for QA - Design: Contact center guide; maybe My VA sketch file clean up - FE: Error states; user testing updates | Medical copays - PM/Design: Have planning discussion
Sprint 68 (2/23 - 3/8) | QA - PM: Analytics request (Look at what we set for KPIs to give Heather details on what she should include in this request; add yo exisiting My VA dashboard) - QA (doesn't need to be day 1 of the sprint) - UAT planning | Medical copays PM: Fill out collab kickoff ticket, but clarify we likely won't need more than a design review and maybe research review Design: Discovery; design exploration
Sprint 69 (3/9 - 3/22) | PRE LAUNCH!! This assumes call center guide is all done. - PM: Make sure analytics updates get implemented; Put together launch plan; Prep fors taging review; Hold staging review if we don't need to do any significant updates from QA (can be towards the end of the sprint if necessary) - Design: Updates from QA, if applicable - FE: Updates from QA if applicable; Prep for privacy and security review - BE: Prepare any technical diagrams or other documentation needed for the privacy and security review | Medical copays PM: ? Design: Finish design explorations; Hold design intent if it didn't already happen; Research planning and prep -- are we doing a "mock" A/B test? Getting feedback during payment UAT? Both?
Sprint 70 (3/23 - 4/5) | Pre-launch prep - If all updates from QA are done, Recruit for and hold UAT - Staging review if we couldn't hold it last sprint; privacy and security review | Get feedback on design in payment UAT; Other research?
Sprint 71 (4/6 - 4/19) | Launch to 25% & 50% | Research?
Sprint 72 (4/20 - 5/3) | Launch to 100% | QA if needed; Analytics request; Pre-launch reviews
Sprint 73 (5/4 - 5/17) | Observe stats after launch | Pre-launch reviews
Sprint 74 (5/18 - 5/31) | Submit for 508 review | Launch

## Alerts
On-site notifications MVP
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | PM: Meet with VANotify Design: Finalize MVP design; meet with VANotify; meet with IA; finalize MVP notification list. FE: Support as needed. BE: Talk to platform; Technical diagram;
Sprint 59 (10/20 - 11/2) | Kickoff collab cycle; start build PM: Collab cycle kickoff; Collab cycle design intent; meet with VANotify Design: Design intent; content; meet with VANotify FE: Meet with VANotify BE: Start build ; meet with VANotify
Sprint 60 (11/3- 11/16) | Finalize designs, if possible; Determine next steps and timeline for VANotify; Continue build PM: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates Design: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates; Finalize designs, if not already done; Work with content, if not already done FE: Work with team to define requirements for VANotify updates; Support team as necessary BE: Work with team to define requirements for VANotify updates; Continue build
Sprint 61 (11/17 - 11/30) | Revisit this work - Talk to Chris and make sure that pivoting is OK - Redefine MVP (elevate all appointments, messages, debt?; Maybe just elevate appointments?) - PM: Given this pivot, do we need to redo any of the collab cycle? - Tressa: Mockup/explorations
Sprint 62 (12/1 - 12/14) | Project on hold
Sprint 63 (12/15 - 12/28) | Resume project - Define needs for VANotify, determine what they need to do, and determine timeline for any work they need to do. - Figure out what design needs to be updated; Update design; determine if we need additional user testing or not based on updates; follow-up with collab cycle design intent issues/tickets and let them know about our pivot. - Determine next steps for backend build; If possible, Tom can start to implement build if possible | Research - Midpoint review - Finish design if not already done - Research planning/convo guide - Start FE build? Finish backend build.
Sprint 64 (12/29 - 1/11) | Start build - PM: Determine VANotify's timeline based on availability; Determine QA/testing strategy -- talk to Leah/Denise/Maria about this; Midpoint review prep (note: testing for this is going to happen as part of payment info testing) - Design: Research prep is happening as part of payment info - FE: Start FE build if possible - BE: Lihan to meet with VANotify to determine how the backend should receive data from VANotify; Start build | Research - Conduc research/summarize research if needed - Continue/finish FE build - QA prep
Sprint 65 (1/12 - 1/25) | Hold midpoint review - PM: Midpoint review - Design: Research (as part of payment info work) - FE: Is there anything that still needs to happen? - BE: Build -- how many sprints? -- Is VANotify going away again because of contract issues? | Finish build - Contact center guides - Finish build
Sprint 66 (1/26 - 2/8) | Continue BE build as necessary Are we on hold until VANotify can work on this?
Sprint 67 (2/9 - 2/22) | On hold until VANotify is available
Sprint 68 (2/23 - 3/8) | On hold until VANotify is available
Sprint 69 (3/9 - 3/22) | 3/15: Intro work to the new VANotify team PM: Regroup with VANotify on this work and determine what next steps are for them; determine timelines for VANotify and FE work FE: Connect FE to backend API Lihan created
Sprint 70 (3/23 - 4/5)
Sprint 71 (4/6 - 4/19) | QA; Analytics request
Sprint 72 (4/20 - 5/3) | Pre-launch prep
Sprint 73 (5/4 - 5/17) | Pre-launch prep
Sprint 74 (5/17 - 5/31) | Launch to 25% & 50%
Launch to 100%

## Profile_LGBTQ data
Personal information updates (LGBTQ data)
Sprints | Planned tasks | Notes
Sprint 58 (10/6 - 10/19) | Team onboards - Meet with team - Collab cycle kickoff - Collab cycle design intent - Create tickets for design, content, and frontend - Get relevant data points (ie What is populating dropdown menus?) - Complete initial mockups
Sprint 59 (10/20 - 11/2) | Continue design and FE build PM: Collab cycle IA review; Create frontend documentation as designs are finalized Design: Meet with content and update designs accordingly FE: Continue frontend build
Sprint 60 (11/3- 11/16) | PM: Continue to work behind the scenes to collab with MPI to get work ready for backend development Design: Transition call with Kevin; Update designs, if needed; Usability research plan FE: Continue build BE: Sit in on MPI calls
Sprint 61 (11/17 - 11/30) | PM: Start putting together list of test cases; Prep for midpoint review Design: Usability research plan & convo guide FE: Continue build (how much longer is this going to take?) BE: Start backend integration if MPI is ready
Sprint 62 (12/1 - 12/14) | Midpoint review, Recruit for user testing, Start testing (?) continue FE build; BE build (tickets TBD after we talk to this team on Wednesday) | Unclear when we'll be able to start backend build
Sprint 63 (12/15 - 12/28) | Recruit for testing if possible - Recruit for testing if contract is back - Continue whatever is left of the frontend build
Sprint 64 (12/29 - 1/11) | Research - PM: ? - Design: Conduct research; Synthesize test results - FE: Continue FE Build - BE: Start BE build
Sprint 65 (1/12 - 1/25) | Finish research; determine next steps with build based on VA Profile's direction - Summarize research - Any FE tasks? - Start BE build if possible
Sprint 66 (1/26 - 2/8) | Design: Changes from research FE: Work on changes from research, if changes are mocked up before the end of the sprint BE: Still on hold
Sprint 67 (2/9 - 2/22) | PM: When will we be ready for QA? Design: Finish all design updates FE: Implement design updates BE: Start BE build if possible; VA Profile is targeting 2/14 for being ready for us
Sprint 68 (2/23 - 3/8) | Continue build; Finish design; Finish FE PM: If content isn't done, assess when we think that will be done based on Danielle's availability; If time, work on contact center guide Design: Finish all design updates; If time, work on contact center guide FE: Finish FE if possible BE: Provide estimate of how long BE build will take; Continue BE build
Sprint 69 (3/9 - 3/22) | Design: Finish design if it's not done; If done, contact center guide FE: Finish any updates if they are not already done; If done, project is on pause for Adam until backend is ready to connect to frontend BE: Continue BE (Tom out 3/10, 11, 14)
Sprint 70 (3/23 - 4/5) | Finish BE - PM: Request QA; Finish all QA prep - Design: UAT planning - BE: Finish BE
Sprint 71 (4/6 - 4/19) | Connect FE to BE
Sprint 72 (4/20 - 5/3) | Connect FE to BE
Sprint 73 (5/4 - 5/17) | QA; Analytics request; Launch plan
Sprint 74 (5/18 - 5/31) | Pre-launch prep
Sprint 75 (6/1 - 6/14) | Pre-launch prep/UAT
Sprint 76 (6/15 - 6/28) | Launch to 25% & 50%
Sprint 77 (6/29 - 7/12) | Launch to 100%

## Profile_Bad address
Bad address indicator
Sprints | Planned tasks | Notes
Sprint 65 (1/12 - 1/25) | PM/PO prediscovery; BE to review swagger docs
Sprint 66 (1/26 - 2/8) | Continue PM discovery; product outline
Sprint 67 (2/9 - 2/22) | Collab cycle kickoff; If time allows with personal info work, start design brainstorming
Sprint 68 (2/23 - 3/8) | Design: Tickets for design in profile and email
Sprint 69 (3/9 - 3/22) | Design intent PM: Intro work to VANotify; determine what they need to do, if anything. Probably something given that we want to send an initial email blast and then emails for users when the bad address indicator gets added. Design: Design if not done the previous sprint; Design intent; Work with content on profile/email copy; start FE documentation on when the alert shows in the profile and when the email will be sent out (initial blast; whenever a new bad address is added)
Sprint 70 (3/23 - 4/5) | Start FE work in profile PM: Midpoint review prep; Start on QA use cases (this will not be completed yet); Figure out how we can get a staging user with the bad address indicator for testing (might require working with VA Profile) Design: Finish FE documentation; Research prep FE: Assuming Design work is done for profile, start FE build (including connecting to BE Tom already built)
Sprint 71 (4/6 - 4/19) | Midpoint review PM: Hold midpoint review Design: Recruit/conduct BE: BE work on email blast/individual emails
Sprint 72 (4/20 - 5/3) | Design: Summarize research
Sprint 73 (5/4 - 5/17) | PM: QA Prep Design: Updates from research, if applicable; Contact center guide FE: Updates from research, if applicable BE: Updates from research, if applicable
Sprint 74 (5/18 - 5/31) | QA PM: Analytics request Design: UAT prep and planning QA: Hold QA
Sprint 75 (6/1 - 6/14) | Updates from QA if applicable; Prep for staging & privacy reviews
Sprint 76 (6/15 - 6/28) | Staging review; Privacy review
Sprint 77 (6/29 - 7/12) | Launch to 25% & 50%
Sprint 78 (7/13 - 7/26) | Launch to 100%
Sprint 79 (7/27 - 8/9)
Sprint 80 (8/10 - 8/23)

## MHV_VA.gov profile research
MHV/VA.gov Profile research
Sprints | Planned tasks | Notes
Sprint 65 (1/12 - 1/25) | Talk to Lauren/Tracey/Meg
Sprint 66 (1/26 - 2/8) | Samara: Outline rough research plan; If it seems like research can happen soon, get Chris on board.
Sprint 67 (2/9 - 2/22) | Chris to talk to MHV and make intros
Sprint 68 (2/23 - 3/8) | Liz to start research planning (if Liz isn't needing to do UAT planning for payments) --> this is only per availability, and note that we haven't been intro'd to MHV yet (but hopefully will soon)
Sprint 69 (3/9 - 3/22) | Conduct all stakeholder interviews (MHV + VA.gov)
Sprint 70 (3/23 - 4/5) | User research prep
Sprint 71 (4/6 - 4/19) | User research interviews
Sprint 72 (4/20 - 5/3) | Liz to deliver final report

## Profile_Military service info
Military service info
Sprints | Planned tasks | Notes
Sprint 66 (1/26 - 2/8) | Samara does discovery; Submits intake form; Maybe initial convos with VA Profile
Sprint 67 (2/9 - 2/22) | Still waiting to hear back from VA Profile
Sprint 68 (2/23 - 3/8) | Still waiting to hear back from VA Profile
Sprint 69 (3/9 - 3/22) | Project planning; Collab cycle kickoff; product outline
Sprint 70 (3/23 - 4/5)
Sprint 71 (4/6 - 4/19)
Sprint 72 (4/20 - 5/3)
Sprint 73 (5/4 - 5/17)

## LT project planning
Long term planning until end of contract
Project | Sprint 67 (2/9 - 2/22) | Sprint 68 (2/23 - 3/8) | Sprint 69 (3/9 - 3/22) | Sprint 70 (3/23 - 4/5) | Sprint 71 (4/6 - 4/19) | Sprint 72 (4/20 - 5/3) | Sprint 73 (5/4 - 5/17)
My VA
Payment updates | Finish design/FE build | QA | Updates from QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
Single on-site notification MVP (Debt notification) | On hold | TBD | TBD | TBD | TBD | TBD | TBD
Profile
Personal information updates | Start BE build | Finish BE build | QA | Updates from QA | Pre-launch | Launch 25 - 50% | Launch 100%
Bad address indicator | Design discovery | Design | TBD | TBD | TBD | TBD | TBD

## Planning by person
Planning by person
Sprints | Tressa | Liz | Christina | Taylor | Adam | Lihan | Tom
Sprint 63 (12/15 - 12/28) | My VA payments work; On-site alerts updates, if applicable | Start transition to take over My VA work; out most of sprint but needs something | Research recruiting; out most of the sprint; needs more work | View Payments technical discovery | Personal information updates | Out; then hopefully can start on MPI work if possible; otherwise, on hold with all work | Onboarding; Can we start him on the VANotify integration? Andre should assign him to help another team
Sprint 64 (12/29 - 1/11) | Tressa's last sprint; Research planning for payment info | Personal info research; continue taking over My VA from Tressa; Finish "benefits you might be interested in updates" if not done | Personal info research | View payments build; On-site notifications MVP build; Benefits you might be interested in update | Personal information updates | Resolve direct deposit issues; On-site notifications build | Resolve direct deposit issues; Personal info build
Sprint 65 (1/12 - 1/25) | Rolling off team | Payment history/on-site notifications research | Personal info research summary; likely needs more work | Likely needs more work | Likely needs more work | Start on on-site notifications build, if possible | Start on personal info build, if possible
Sprint 66 (1/26 - 2/8)
Sprint 67 (2/9 - 2/22)
Sprint 68 (2/23 - 3/8)
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings