## Sheet1
Issue | Recommentations from Research Report | Team Ideas & Discussion | Relevant Team(s) | Decision/Next Steps
Many people aren't finding the Resources & support link in the footer | consider providing additional links in the header where more people will see it (i.e., "Resources" or "Help"). | need to work on strategy for post-beta R&S | Sitewide Content/IA, Benefit hubs
Many people aren't finding the Find a Form link in the footer | consider putting a Forms link into the header somewhere | Meg is open to making Forms prominent in the header. also part of search tools redesign--how to surface these other tools | Sitewide Content/IA, Search & Discovery
People spend so much time looking at links in the "top 4" boxes and not elsewhere on the home page | consider adding additional links and/or a "View more" link in each box. Additional links to consider are the following: | could consider removing some existing links that aren't used | Sitewide Content/IA
can't find travel pay reimbursement info | Travel pay reimbursement (add to Health care box and VA Benefits and Health Care megamenu under health care and/or disability) | travel reimbursement is not only for medical appointments but also for claim exams or compensation & pension exams, so maybe also need a link elsewhere Meg is looking at a financial "hub" for Veterans--maybe put a link there | Sitewide Content/IA, Digital Health Modernization team
can't find direct deposit info | Update direct deposit (add to Records box) |  | Sitewide Content/IA
can't find medical records info | Medical records (add to the Health care box, in addition to Records) |  | Sitewide Content/IA, Digital Health Modernization team
can't find how to update dependents | Update dependents (add to Records box and also on the Family Member Benefits page) |  | Sitewide Content/IA
can't find form to appoint a representative | Appoint representative (add to Disability box) |  | Sitewide Content/IA, Digital Health Modernization team
can't find VA forms | VA forms (add to Disability box) | Marci: forms are across VA, not just Disability | n/a | don't do
site search isn't noticed by many people | consider adding a search box next to the word Search in the header and/or just above or below the "top 4" boxes. | Search & Discovery has an epic about moving around Search and improving its presentation. Megan working on designs | Search & Discovery, Sitewide Content/IA | epic already created
site search queries scroll off the end of the box | consider making the search box wider |  | Search & Discovery
search results not relevant | Is site search indexing all of the content accessible via Find a Form, Resources & support, and Find a VA Location? Should make sure they show up in the search results so we can ensure that we are returning all relevant results from VA.gov. |  | Search & Discovery
many people don't scroll down below the row of pictures | Consider moving the row of images down to the actual bottom of the page so it doesn't give a false "bottom of the page" signal in the middle of the page. |  | Sitewide Content/IA?
many people thought you could get proof of your VA income from View payment history | Consider making it possible to get proof of income in the form of benefit letters from the View payment history page, as well as from site searches for "income" or "proof of income". |  | Sitewide Content/IA?
Find a Form search results not relevant | Work on improving the Find a Form search: | Marci is working on improvements (what specifically?) | Decision Tools
Find a Form search results not relevant | Remove articles and other helper words (e.g., "a", "the", "how do I") from search queries before searching |  | Decision Tools
Find a Form search results not relevant | Search on only the first few words of a long search query |  | Decision Tools
Find a Form search results not relevant | Provide typeahead suggestions for common search queries while entering a search query |  | Decision Tools
Find a Form search results not relevant | Add some fixed links per search query (e.g., a search for "spouse" should return the form to add/update dependents) |  | Decision Tools
COVID banner alert on home page is annoying | Consider making the COVID banner alert on the home page dismissable (as it is on other content pages). |  | Public Websites? Sitewide Content/IA?
COVID banner alert on home page is annoying to screen reader user | accessibility specialist Josh Kim recommends making the alert less annoying to screen reader users by changing the current aria-live attribute from assertive (interrupts user actions) to polite, which tells the screen reader to wait until the user is done to announce updates. |  | Public Websites | ticket already created
Font size in "top 4" boxes is too small for an older participant to read | Consider increasing the font size of the links in the "top 4" boxes from the current 16px to 19px, which is the current recommendation (though not required) for older users, per Josh Kim and our peers (including Gov.uk, NHS, Health Literacy Online), because many of our users are older. We could conduct more research on the VA.gov home page with people age 55-64 or older. |  | Public Websites? Sitewide Content/IA?
Site search is hard to find while using a screen reader | Consider revising the site search box to make it easier to find quickly while using a screen reader by coding search as a landmark role (per Josh Kim and Angela Fowler). |  | Public Websites? Search & Discovery?
Site search results didn't load due to JavaScript that didn't load | Investigate the JavaScript https://dap.digitalgov.gov/Universal-Federated-Analytics-Min.js?agency=VA that didn't load, causing a "your browser is out of date" error message instead of search results. Could watch the session recording to see browser and other details | PW can look into--get session recording and try to recreate the issue (p16 on task 3) | Public Websites
Participant didn't know about any non-texting options to do two-factor authentication for the VA | Consider adding an article to Resources and support about two-factor authentication. See if it's possible to use to select a photo to authenticate like eBenefits does. |  | Sitewide Content/IA?
the header wasn't widely used but could have additional links | Consider conducting further user research on the VA.gov header and potential redesigns on mobile and desktop (especially if add new links to Forms, Resources or Help) to make sure that the most useful links are visible and others are not. |  | Sitewide Content/IA? Public Websites?
Some participants didn't find "Find a VA Location" and instead used search |  | share location results w/Facilities team | Sitewide Content/IA, Facilities?
site search for a location sometime didn't return VAMC's |  | for Type-Ahead, add VAMCs for relevant city searches with a Best Bet link | Search & Discovery