## Slide 1
Veteran-Facing Services – Digital Health Modernization
Kickoff Meeting
20 January 2022
1095-B Tax Form

## Slide 2: Objectives for today
Get to know the team (10 min)
Review 1095-B Project Overview on Mural (1 hour 25 min)
Align on approach (20 min)
Define next steps and wrap up (5 min)
Kick-off: 1095-B Tax Form

## Slide 3: Get to know the team
Ashley Castillo Washington DC Product Manager Lead
Jordan White Dallas, TX Product Manager
Executive Team
*Day to day workiing team will be adjusted through project lifecycle if new skillset needs arise
Tami Corson
North Carolina
Scrum Master
Jeff Scheire
MO Studio
Marcy Jacobs
McKinsey
Jared Cooke Los Angeles, CA Front End Developer
Nadya Primak Washington DC Engineer
Will Reynolds Serve
Carl Dickerson Atlanta, GA Content Strategist and Plain Language Content Creator
Jesse Singh Minneapolis, MN UX Design Lead
Kit Casey Boston, MA Design Director
James Lewis Austin, TX Accessibility and UX Research Lead
Grace Hong New Jersey Experience Designer
Kevin London frog
Ben Morris
Pluribus
Core Team
Product
Design
Engineering
Kick-off: 1095-B Tax Form

## Slide 4: Project objectives
Digitize 1095-B form on va.gov so veterans can view the form, download the form, & be able to upload or print it for their taxes.
Create space on va.gov production, with all steps required for a veteran to download their 1095-B form
Increase availability of self-service tools
For discussion:
1) What is the core pain point we are trying to solve?
2) What is the current state?
3) What is the experience of the future state?
4) What stakeholders or groups are key for us to loop in?
5) What risks or potential challenges do we want to keep an eye on?
Move to Mural Board for discussion
Kick-off: 1095-B Tax Form

## Slide 5
Work plan
1095-B Tax Form

## Slide 6: Our approach to veteran-centered design
Viability
Feasibility
Desirability
User Experience
& Design
Engineering & Development
Product & Delivery
A creative problem-solving approach to problem-solving that starts with people and ends with innovative solutions that balance the three lenses.
Kick-off: 1095-B Tax Form

## Slide 7: Workplan overview
Week 1: 01/20 – 01/26
Sprint 0
Week 3: 02/02 – 02/09
Week 4: 02/09 – 02/16
Week 5: 02/16 – 02/23
Week 6: 02/23 – 03/02
Week 7: 03/02- 03/09
Week 9: 03/16 – 03/23
Week 8: 03/09 – 03/16
Week 2: 01/26–02/02
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Week 10: 03/23 – 03/30
Sprint 5
Staging Deployment
POC for data flow
Test & Refine
Create tech discovery plan
Immersion & onboarding
Immersion & onboarding
Product & Delivery
Engineering & Development
Voice of Veteran
Voice of Veteran
Voice of Veteran
Immersion & onboarding
PIV Onboarding
User Experience & Design
Product roadmap
Create Change Management or Communications Plan
Handover plan implementation; prepare for launch
Build backlog
Product Launch Collaboration Cycle (as needed)
Data discovery
Build solution (form and data connections, storage, etc.)
UAT
Define data flows - Systems mapping
User flows
Testing prep & recruiting
Testing prep & recruiting
Testing prep & recruiting
Design iterations
PIV Onboarding
Wireframes & Design
Design iterations
Create post-MVP design refinements
Design QA
MVP Launch
Collaboration Cycle
Let’s discuss touchpoints

## Slide 8
Scrum cadences
1095-B Tax Form

## Slide 9: Calendar overview
02
01
28
04
03
26 Sprint 0 End;
Sprint 1 Start
25
24
28
27
19
18
17
21
20 Project Kick Off
09 Sprint 1 Demo; Sprint 2 kickoff
08
07
11
10
23 Sprint 2 Demo; Sprint 3 kickoff
22
21 President’s Day Holiday
25
24
02
01
31
04
03
09 Staging Deployment; Sprint 3 Demo; Sprint 4 Kick Off
08
07
11
10
16
15
14
18
17
23 Sprint 4 Demo; Sprint 5 Kick Off
22
21
25
24
Wednesday
Tuesday
Monday
Friday
Thursday
16
15
14
18
17
January
February
March
02/27
01/23
01/16
02/06
02/20
01/30
03/06
03/13
03/20
Week of
02/13
03/27
30
29
28
April 1 MVP Launch
31
We are here
Launch
Kick-off: 1095-B Tax Form

## Slide 10: Each sprint runs two weeks, starting on Thursdays
12:00 – 1:00 PM
09:00 – 10:00 AM
Monday
Wednesday
Sprint Planning
10:00 – 11:00 AM
Friday
Thursday
Tuesday
Wednesday
Thursday
Friday
Monday
Sprint Retro
11:00 – 12:00 AM
Daily Standup
Sprint Demo
Daily Standup
Daily Standup
Daily Standup
Daily Standup
Daily Standup
Daily Standup
Daily Standup
Daily Standup
Backlog Grooming (Internal)
PO Sync
3:00 – 4:00 PM
2:00 – 3:00 PM
1:00 – 2:00 PM
PO Sync
Backlog Grooming (with stakeholders)
PO Sync
Backlog Grooming (Internal)
PO Sync
Tuesday
4:00 – 5:00 PM
Demo prep
Design Review
Design Review
Design Review
With core team only
With VA-PO
With VA-PO and stakeholders
*Sprint cadence shown is example; team to align with VA-PO and stakeholders and confirm all dates/timings before sending invites
Note: Timing subject to change based on availability
Kick-off: 1095-B Tax Form

## Slide 11: Meetings with Tracey or stakeholders outside of core team
Meeting | Attendees | Objectives | Outputs
PO Sync | Tracey, Jordan, Ashley, Kit (optional) | Align with Tracey on upcoming sprint goals and latest roadmap Review sprint progress for this sprint thus far Get directional guidance on key questions | Refined sprint goals Updated roadmap Prioritized backlog to be taken into next sprint planning
Design Review | Tracey, Kit, Grace, Jesse, James, Jared, Ashley (optional) | Present latest designs in this sprint Get feedback from Tracey | Feedback that can be turned into user stories for design and prioritized
Sprint Demo | Tracey, full working team, all stakeholders invited | Present all work accomplished in this current sprint for feedback | Feedback from stakeholders turned into user stories that can be prioritized for upcoming sprints
Backlog Refinement | Tracey, Kit, Jordan, additional team members as needed based on story, key stakeholders TBD | Discuss stories, designs, or work to be done in upcoming sprints to refine the user story | User stories for future sprints are updated, meet Definition of Ready, and can be pulled into future sprints
Meeting
Attendees
Objectives
Outputs
To discuss work in the current sprint
PO Sync
Tracey, Jordan, Ashley, Kit and/or Jesse (optional)
Align with Tracey on upcoming sprint goals and latest roadmap
Review sprint progress for this sprint thus far
Get directional guidance on key questions
Refined sprint goals
Updated roadmap
Prioritized backlog to be taken into next sprint planning
Design Review
Tracey, Kit, Grace, Jesse, James, Jared, Ashley (optional)
Present latest designs in this sprint
Get feedback from Tracey
Feedback that can be turned into user stories for design and prioritized
Sprint Demo
Tracey, full working team, all stakeholders invited
Present all work accomplished in this current sprint for feedback
Feedback from stakeholders turned into user stories that can be prioritized for upcoming sprints
To discuss work for future sprints
Backlog Grooming with stakeholders
Tracey, Kit, Jordan, Jesse, additional team members as needed based on story, key stakeholders TBD
Discuss stories, designs, or work to be done in upcoming sprints to refine the user story
User stories for future sprints are updated, meet Definition of Ready, and can be pulled into future sprints
Kick-off: 1095-B Tax Form

## Slide 12
Next steps
1095-B Tax Form

## Slide 13: Next steps
Discuss any revisions to workplan and current sprint progress at first PO Sync on Tuesday 1/25
Align on next sprint’s goal with Tracey and kick off next sprint on Wednesday 1/26
Decide on attendees for sprint demos and backlog refinements and send invites by Friday 1/28
Kick-off: 1095-B Tax Form

## Slide 14
Appendix

## Slide 15: Roles and responsibilities
Role | Responsibility | Name | Organization
Executive Sponsors | Continuously sponsor and guide team in defining and delivering to the project goals and scope. Champion the product within the larger ecosystem. Make connections to inform the product and help the product team engage stakeholders at the right times. | Lauren Jeff | OCTO MO
Product Owner | Work with product team to generate and prioritize user stories based on research. Make decisions and help manage product activities in collaboration with Product Manager (e.g., provide guidance, remove blockers, collaborate in developing the requirements, schedule, and vision, connect with SMEs). Review, approve, and accept products, deliverables and recurring reports (Delivery Reports; Monitoring Reports; Progress, Status and Management Reports; Status of GFE Reports; Personnel Contractor Manpower Reports; Contractor Staff Rosters). | Tracey | OCTO
COR | Review, approve, and accept work performed and recurring reports (Delivery Reports; Monitoring Reports; Progress, Status and Management Reports; Status of GFE Reports; Personnel Contractor Manpower Reports; Contractor Staff Rosters). Review T&M requests as appropriate. Support Program Manager with VA onboarding and invoicing as required. | Mary /Vilay | OCTO
Program Manager | Accountable leader for the overall program. Define strategy and define features; manage stakeholders. Responsible for reporting and compliance. Cultivate a positive, trusting, and cooperative working relationship with the Government and all other vendors supporting this work. Responsible for future state journey / vision. | James | MO
Product Manager | Ultimate decision maker for the product. Has working knowledge across capabilities (research, design, dev) and product development lifecycle. | Jordan/Ashley | MO/McKinsey
Delivery Manager | Maintain a consistent look, feel, and voice across user facing sites and services. Incorporate best practices defined in the VA Design System and VA Content Style Guide (https://design.va.gov/). Support the design team in activities including content creation, workshop preparation, facilitation, interaction design, synthesis, and others as needed. | Carl | MO
Business Analyst | Business expert that has deep understanding of current state journey. Typically 10+ years experience across lines of business. | Tami | SERVE Advisory
CLIN 0001AC
Role
Organization
Responsibility
Name
Executive Sponsors
OCTO
MO
Continuously sponsor and guide team in defining and delivering to the project goals and scope.
Champion the product within the larger ecosystem.
Make connections to inform the product and help the product team engage stakeholders at the right times.
Lauren
Jeff
Product Owner
OCTO
  Work with product team to generate and prioritize user stories based on research.
  Make decisions and help manage product activities in collaboration with Product Manager (e.g., provide guidance, remove blockers, collaborate in developing the requirements, schedule, and vision, connect with SMEs).
  Review, approve, and accept products, deliverables and recurring reports (Delivery Reports; Monitoring Reports; Progress, Status and Management Reports; Status of GFE Reports; Personnel Contractor Manpower Reports; Contractor Staff Rosters).
Tracey
COR
OCTO
Review, approve, and accept work performed and recurring reports (Delivery Reports; Monitoring Reports; Progress, Status and Management Reports; Status of GFE Reports; Personnel Contractor Manpower Reports; Contractor Staff Rosters).
Review T&M requests as appropriate. Support
Program Manager with VA onboarding and invoicing as required.
Mary/ Vilay
Program Manager
MO
Accountable leader for the overall program.
Define strategy and define features; manage stakeholders.
Responsible for reporting and compliance.
Cultivate a positive, trusting, and cooperative working relationship with the Government and all other vendors supporting this work.
Responsible for future state journey / vision.
James
Product Manager
MO/McKinsey
Ultimate decision maker for the product.
Has working knowledge across capabilities (research, design, dev) and product development lifecycle.
Jordan/ Ashley
Delivery Manager
MO
Maintain a consistent look, feel, and voice across user facing sites and services.
Incorporate best practices defined in the VA Design System and VA Content Style Guide (https://design.va.gov/).
Support the design team in activities including content creation, workshop preparation, facilitation, interaction design, synthesis, and others as needed.
Carl
Business Analyst
Business expert that has deep understanding of current state journey. Typically 10+ years experience across lines of business.
Tami
SERVE Advisory
Kick-off: 1095-B Tax Form

## Slide 16: Roles and responsibilities
Role | Responsibility | Name | Organization
Design Lead | Lead and guide the design team. Work with Product Manager to develop and scope work and lead the design team to deliver at the highest performance and consistency for research, UX design, and visual design. Ensure accessibility is considered throughout the design process. Collaborate with multidisciplinary product teams and government staff, facilitate workshops, and lead with agility. | Kit | Frog
UX Designer | Turn research insights into design decisions; designs end-to-end UX based on user research; includes accessibility and service design. Personalize solutions for the individual or team using the product. Support the design team in activities including content creation, workshop preparation, facilitation, interaction design, synthesis, and others.Maintain a consistent look, feel, and voice across user facing sites and services. Create assets including navigation designs, wireframes, information architecture diagrams, design prototypes. Maintain a high level of quality and consistency and conducts site audits. Ensure all work products from the team are in line with brand standard including presentations and murals. Incorporate best practices defined in the VA Design System and VA Content Style Guide (https://design.va.gov/) Research customer behavior and common customer responses to particular experiences Design services to improve customer experience. | Jesse/Grace | MO/frog
Content Strategist/ Plain Language Writer | Write new content following the guidelines in the content style guide; understanding of relationship between content and accessibility (or access to accessibility experts). Content strategy, copy editing and storytelling responsibility for user facing materials and work product. | Carl | MO
Backend Engineer | Design, build, and maintain the server side of the application. Build the structure of the software application. | TBD | Pluribus
Design Lead
Lead and guide the design team.
Work with Product Manager to develop and scope work and lead the design team to deliver at the highest performance and consistency for research, UX design, and visual design.
Ensure accessibility is considered throughout the design process.
Collaborate with multidisciplinary product teams and government staff, facilitate workshops, and lead with agility.
Kit/Jesse
Frog/MO
UX Designer
Turn research insights into design decisions; designs end-to-end UX based on user research; includes accessibility and service design.
Personalize solutions for the individual or team using the product.
Support the design team in activities including content creation, workshop preparation, facilitation, interaction design, synthesis, and others. Maintain a consistent look, feel, and voice across user facing sites and services.
Create assets including navigation designs, wireframes, information architecture diagrams, design prototypes.
Maintain a high level of quality and consistency and conducts site audits.
Ensure all work products from the team are in line with brand standard including presentations and murals.
Incorporate best practices defined in the VA Design System and VA Content Style Guide (https://design.va.gov/)
Research customer behavior and common customer responses to particular experiences
Design services to improve customer experience.
Grace
Frog
Content Strategist/ Plain Language Writer
Write new content following the guidelines in the content style guide; understanding of relationship between content and accessibility (or access to accessibility experts).
Content strategy, copy editing and storytelling responsibility for user facing materials and work product.
Carl
MO
Backend Engineer
Design, build, and maintain the server side of the application.
Build the structure of the software application.
Nadya
Pluribus
Role
Organization
Responsibility
Name
Kick-off: 1095-B Tax Form

## Slide 17: Roles and responsibilities
Role | Responsibility | Name | Organization
Data Engineer | Design, develop, optimize, and maintain data architecture and pipelines that adhere to ETL principles and business goals Foster a culture of sharing, re-use, design for scale stability, and operational efficiency of data and analytical solutions Solve complex data problems to deliver insights that helps the organization's business to achieve their goals Partner with business analysts and solutions architects to develop technical architectures for strategic enterprise projects and initiatives. | TBD as needed | TBD
Data Architect | Design end to end analytical workflows, including overall architecture, capabilities, platforms, tools and governing processes Create, maintain, and communicate positioning/go-forward strategies for analytical capabilities/tools Share governance responsibility to ensure alignment to enterprise guidelines for security, auditability, data governance, metadata management, etc. Help define/improve best practices, guidelines and integration with other enterprise solutions Create and evolve analytic technology roadmap, to align with continuously evolving business needs | TBD as needed | TBD
Interaction Designer | Determine customer needs and define product interactions necessary to achieve them. Compile user, business and technical requirements to create product information architecture. Create wireframes and prototypes that illustrate key product interactions. | Jared/James | MO/frog
QA Testing | Use automated testing frameworks to create unit tests, integration tests, functional/black box tests, and load tests (or their equivalents as applicable) to test 100% of functionality delivered. Strive for compliance with Test Driven Development practices. Ensure configuration and sensitive data, including data the VA defines as sensitive, are not present in source code, and are stored in encrypted credential management systems. | Nadya | Pluribus
Frontend Developer | Optimize web applications for mobile-first operation, with all solutions being equally available on both mobile and desktop whenever possible. Incorporate robust accessibility principles into design, development and testing for all web applications to deliver high-quality digital experiences to users of assistive devices. Accessibility testing while coding | Nadya | Pluribus
Interaction Designer
Determine customer needs and define product interactions necessary to achieve them.
Compile user, business and technical requirements to create product information architecture.
Create wireframes and prototypes that illustrate key product interactions.
James
Frog
QA Testing
Use automated testing frameworks to create unit tests, integration tests, functional/black box tests, and load tests (or their equivalents as applicable) to test 100% of functionality delivered.
Strive for compliance with Test Driven Development practices.
Ensure configuration and sensitive data, including data the VA defines as sensitive, are not present in source code, and are stored in encrypted credential management systems.
Nadya
Pluribus
Frontend Developer
Optimize web applications for mobile-first operation, with all solutions being equally available on both mobile and desktop whenever possible.
Incorporate robust accessibility principles into design, development and testing for all web applications to deliver high-quality digital experiences to users of assistive devices.
Accessibility testing while coding
Jared
MO
Role
Organization
Responsibility
Name
Kick-off: 1095-B Tax Form

## Slide 18: Project management deliverables
Expected delivery
Deliverable
Owner
Status
NLT the 7th day of the month following each reporting period.
Delivery Report
(a) Gov’t Product Owner agrees that the Contractor provided a monthly report, detailing and providing links to all stories, epics, and other work completed.
(b) Report includes all work accepted by the Product Owner and Contracting Officer Representative at the end of each sprint.
(c) This report includes additional details about the project status, sprint team velocity, sprint team goal completion, and highlight project risks.
MO
NLT the 7th day of the month following each reporting period.
Monitoring Report
(a) Gov’t Product Owner agrees that the Contractor provided a monthly report, highlighting and providing links to key infrastructure and application monitoring data.
(b) Report includes details with links to documentation for any critical incidents or outage events that resulted in service outages or significant service degradations.
(c) Contractor attached or provided links to postmortem documentation for all critical incidents or outage events.
MO
Not Started
NLT the 7th day of the month following each reporting period.
Contractor’s Progress, Status and Management Report
Gov’t Product Owner agrees that the status of the Task Orders performance has been addressed in the Quarterly Status Report.
MO
Not Started
Not Started
Acceptance criteria
Kick-off: 1095-B Tax Form

## Slide 19: Project management deliverables
Expected delivery
Deliverable
Acceptance criteria
Owner
Status
NLT the 7th day of the month following each reporting period.
Status of Government Furnished Equipment Report
Gov’t Product Owner agrees that the GFE Report includes the following items related to GFE: Task Order; Project Name, Type of Equipment, VA Bar Code, Location, Value, Total Number of Pieces, Total Value of Equipment, Anticipated Transfer Date to Government, and Anticipated Transfer Location.
MO
Not Started
NLT the 7th day of the month following each reporting period.
Personnel Contractor Manpower Report
Gov’t Product Owner agrees that the Personnel Contractor Manpower Report at the individual Task Order Level includes all of the required information outlined in the Base PWS section 9.2.3.
MO
Not Started
Within 3 days from the date of award and updated as personnel changes throughout the PoP.
Contractor Staff Roster
Gov’t Product Owner agrees that this report includes all Contractor and Subcontractor employees and was provided within three business days after Task Order award for all personnel employed to begin their background investigations. A revised roster will be provided when there are any personnel changes.
MO
Complete
Within 10 business days of each sprint.
Sprint plan for each sprint
Gov't Product Owner agrees that the goals for each iteration have been met.
OCTO
Not Started
Kick-off: 1095-B Tax Form

## Slide 20: Each element of the process is supported by a meeting, with clear inputs and outputs
Ceremony
Outputs
Inputs
Activities
  Sprint Planning
    Confirmed Sprint goal
    Confirmed Sprint backlog
    Sprint plan, with stories estimated and broken down as needed
    Team capacity
    Planning velocity
    Prioritized Product Backlog
    Sprint goal
    Sprint backlog
    Review prioritized backlog
    Elaborate stories
    Review sprint goal
    Estimate tasks based on development best practices
    Consider high-level design
  Daily Stand-Up
    Updated release board
    List of impediments to resolve
    Release board
    List of priorities for the day
    Questions for PO
    Answer the following questions:
      What I did yesterday
      What I will do today
      What impediments I have
  Sprint Demo
    Signed off stories
    Improvements
    New stories
    Potentially shippable increment of software and most recent accomplishments
    Updated release plan
    Demonstrate the stories developed in the sprint
    Discuss feedback
    Create new stories as needed based on feedback
    Update on release progress
  Sprint Ret-rospective
    Actions for improvement
    Sprint metrics
    Discuss sprint
    Identify what went well or didn’t during th sprint
    Identify actions for improvement
  Backlog Grooming
    Updated and prioritized product backlog
    Technical spikes
    Business spikes
    Up to date feedback from sprint review
    Feedback from users
    Discuss new stories for the backlog
    Review stories and acceptance criteria with the team
    Estimate stories
  PO Sync
    Questions from core team
    Latest roadmap
    Resolve current questions from the team
    Review latest roadmap and align on potential changes
    Discuss upcoming sprints and draft sprint goals and plans
    Updated and prioritized product roadmap
Kick-off: 1095-B Tax Form

## Slide 21
Meeting
Objective
Timing
Lead
Sprint Retro
    Timeboxed meeting that takes place after the sprint review and before sprint planning.
    Examine how the just-completed sprint went as far as people, relationships, processes, and tools.
    Identify and order what went well.
TBC
Tami
Jordan, Ashley, Jesse, Jared, Carl, Nadya, Tami, James, Grace, Kit
Backlog Grooming for internal team
    Ensure the backlog remains populated with items that are relevant, detailed and estimated to a degree appropriate with their priority, and in keeping with current understanding of the project or product and its objectives
TBC
Jordan / Ashley
Jordan, Ashley, Jesse, Jared, Carl, Nadya, Tami, James, Grace, Kit,
Daily Standup
    Daily Check in of progress and identifying blockers
TBC
Tami
Jordan, Ashley, Jesse, Jared, Carl, Nadya, Tami, James, Grace, Kit
Sprint Planning
    Kicks off the sprint.
    Define what can be delivered in the sprint and how that work will be achieved.
    Collaboration with the whole scrum team.
TBC
Jordan / Ashley
Jordan, Ashley, Jesse, Jared, Carl, Nadya, Tami, James, Grace, Kit
Attendees
Core team meetings
Kick-off: 1095-B Tax Form

## Slide 22: Scrum utilizes 5 main sprint components to plan for unknown, respond to change and set a rhythm for the team
Sprint Backlog
  Features for a Sprint estimated by team
  Team commitment
Time-boxed Test/Develop
(No changes)
Product Backlog
  User focused prioritized product features
Sprint 0
  Team alignment
  Release planning
Working software ready for deployment
Time-boxed “Sprint” Cycles
  Sprint Planning
    Review product backlog
    Estimate sprint backlog
    Commit
  Daily Stand up
    What did I do yesterday?
    What do I plan to do today?
    What are my impediments?
  Sprint Review
    Demo features to all
    Share key project metrics
  Sprint Retrospective
    Done after each sprint
    Aims to improve the process for next sprint
  Backlog Grooming
    During each sprint
    Socialize up-coming stories with the team
Process:
Meetings:
Product Backlog
  User focused prioritized product features
Kick-off: 1095-B Tax Form