## Sitewide & Formation
Severity | Open Issues | Location | Opened | Where | Maintainer | Audit Status
508-defect-1 — Critical | [FUNCTIONALITY]: Modal - Focus MUST be set correctly on the window for all screen readers - #9231 | Production | 2019-05-18 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-1 — Critical | [SCREENREADER]: Inline error messages are announcing to screen readers on correction, not on subsequent errors - #314 | Production | 2019-06-18 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-2 — Serious | [COGNITION]: Pagination - HTML SHOULD be updated to improve usability for assistive technology - #9183 | Production | 2020-05-15 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-2 — Serious | [SCREENREADER]: Additional Information - VoiceOver MUST set focus correctly when the component is toggled - #8856 | Production | 2020-05-06 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-2 — Serious | [SCREENREADER]: Improve the modal windows to prevent AT users from navigating page behind the window screen - #1449 | Production | 2019-08-29 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-2 — Serious | CMS [COGNITION]: Multiple ambiguities with linked text in content block - #3556 | Production | 2019-11-19 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | [SCREENREADER]: Legends must be first child element of fieldesets for tabbing navigation - #767 | Production | 2019-07-31 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | [SCREENREADER]: JAWS does not announce some sections of the multi-step forms when loaded - #317 | Production | 2019-06-18 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | [SCREENREADER]: Text and inputs added dynamically should be announced by screen readers - #316 | Production | 2019-06-18 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | [KEYBOARD]: main nav accessibility -- tabbing in small screens - #1144 | Production | 2019-08-20 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | sitewide, design system, CMS [AXE-CORE]: Heading levels SHOULD increase by one - #7708 | Production | 2020-04-07 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | CMS, components, design system [KEYBOARD]: Landmarks MUST have a unique role or role/label/title (i.e. accessible name) combination; main nav and sidebar nav conflict - #7723 | Production | 2020-04-07 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | sitewide, design system, CMS [AXE-CORE]: Heading levels should increase by one - #7755 | Production | 2020-04-07 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | CMS, components, design system [SCREENREADER] Aside MUST not be contained in another landmark - #7844 | Production | 2020-04-10 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | sitewide, design system, CMS [AXE-CORE]: Heading levels SHOULD increase by one, On this page component - #7877 | Production | 2020-04-10 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-2 — Serious | sitewide, design system, CMS [AXE-CORE]: Heading levels SHOULD increase by one, On this page component - #7877 | Production | 2020-04-10 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-3 — Minor | [COGNITION]: Sortable Table - Buttons MUST look like clickable UI elements - #9193 | Production | 2019-05-18 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-3 — Minor | [COGNITION]: Modals - CONSIDER updating HTML in modal dialogs to increase understanding - #9182 | Production | 2019-05-15 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-3 — Minor | [COGNITION]: Buttons - All buttons SHOULD have a darker shade on hover and focus - #9087 | Production | 2019-05-13 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-3 — Minor | [COGNITION]: Breadcrumbs - Lists SHOULD announce the number of items in VoiceOver - #9085 | Production | 2019-05-13 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-3 — Minor | [COGNITION]: Breadcrumbs - Links SHOULD NOT be announced when component re-renders - #9031 | Production | 2019-05-13 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-3 — Minor | [COGNITION]: Alert Box - Icons SHOULD NOT be invisible tab stops for screen readers - #9028 | Production | 2019-05-13 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-3 — Minor | Update the Additional Info component to be used for Learn More expandable sections in forms - #4330 | Production | 2019-12-18 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-3 — Minor | [SCREENREADER]: Decorative content MUST be implemented in a way it can be ignored by assistive technology - #9113 | Production | 2020-05-14 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-3 — Minor | [SCREENREADER]: Consider updating phone number documentation in design system, to include spacing in the aria-label - #9114 | Production | 2020-05-14 |  |  | Not applicable. Issues should be completed as soon as possible.
508-defect-3 — Minor | sitewide, forms [FOCUS MANAGEMENT]: Focus outline SHOULD be removed from non-linked heading - #9116 | Production | 2020-05-14 | Sitewide |  | Not applicable. Issues should be completed as soon as possible.
508-defect-3 — Minor | [SCREENREADER, SEMANTIC MARKUP]: aria-label SHOULD be removed when it is redundant - #9134 | Production | 2020-05-14 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-3 — Minor | sitewide, forms 508-defect-3 [SCREENREADER]: Decorative content MUST be implemented in a way it can be ignored by assistive technology - #9169 | Production | 2020-05-15 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-3 — Minor | sitewide 508-defect-3 [SCREENREADER]: Progress indicator SHOULD be consistent on the same page - #9226 | Production | 2020-05-18 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-3 — Minor | sitewide, forms 508-defect-3 [FOCUS MANAGEMENT]: Focus outline SHOULD be removed from non-linked heading - #9218 | Production | 2020-05-18 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | Create research code samples for better accordion usability with screen readers, assistive technology - #4706 | Production | 2020-01-09 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-4 — Trivial | Consider building two On This Page components for in-page anchor links - #5125 | Production | 2020-01-09 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-4 — Trivial | [IMPROVEMENT]: Formation - CONSIDER making Featured Content heading dynamic - #8352 | Production | 2020-04-23 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-4 — Trivial | [IMPROVEMENT]: Address Block - CONSIDER adding a component and structured data - #8859 | Production | 2020-05-06 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-4 — Trivial | [FUNCTIONALITY] Sortable Table - SHOULD provide a sorting function - #9194 | Production | 2020-05-18 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-4 — Trivial | [COLORBLINDNESS]: Buttons - CONSIDER adding a non-color element to differentiate primary from default - #9141 | Production | 2020-05-13 | Formation Design System | VSP | Audit underway by VSP as of May 2020.
508-defect-4 — Trivial | [AXE-CORE]: Heading levels SHOULD increase by one - #9115 | Production | 2020-05-14 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | [EXPLORATION]: Turn on jsx-a11y ESLint rules - #1139 | Production | 2019-08-20 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | [EXPLORATION]: Disable known buggy axe rules individually - #1140 | Production | 2019-08-20 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | [EXPLORATION]: Reconsider structure of multiple pages within a single "part" of a form - #1145 | Production | 2019-08-20 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | Implement utility class for removing gold outline during focus - #457 | Production | 2019-07-01 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | [USABILITY]: Application saved message could be missed by assistive devices - #182 | Production | 2019-07-01 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | [SCREENREADER]: VA is read phonetically instead of as the abbreviation - #4507 | Production | 2020-01-02 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | [SCREENREADER]: JAWS + Chrome enables focus mode when we focus breadcrumb UL on page load - #319 | Production | 2019-06-18 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | [SCREENREADER]: Review sections with no header cause aria-label errors - #318 | Production | 2019-06-18 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | [SCREENREADER]: VET TEC - NVDA does not read the error if I forget to agree to the privacy policy - #1141 | Production | 2019-08-20 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | CMS [AXE-CORE]: All page content MUST be contained by landmarks - #7757 | Production | 2020-04-08 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | CMS [AXE-CORE]: All page content MUST be contained by landmarks - div.veteran-banner - #7710 | Production | 2020-04-07 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
508-defect-4 — Trivial | design system, components, cms [SEMANTIC MARKUP] Download links SHOULD use the download attribute - #7840 | Production | 2020-04-09 | Sitewide | VSP & VSA | Not applicable. Issues should be completed as soon as possible.
Enhancement | Consider displaying Veterans Crisis Line info in footer on screens 767px wide and smaller - #3459 | Production | 2019-11-18 | Sitewide | VSP | Not applicable. Issues should be completed as soon as possible.