## My VA redesign
My VA redesign: Long term planning
Sprints | Estimate #1: Conservative estimate (though assumes no roadblocks) | Estimate #2: Accelerated timeline | Estimate #3: Super aggressive timeline
Sprint 44 (3/24 - 4/6) | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build
Sprint 45 (4/7 - 4/20) | PM: Assist with call center guide; Thorough review of FE build Design: Start call center guide; Thorough review FE build; FE: Finish build | PM: Assist with call center guide; Thorough review of FE build Design: Start call center guide; Thorough review FE build; FE: Finish build | PM: Assist with call center guide; Thorough review of FE build; Meet with analytics team; Hold go/no-go for QA; Request QA for next sprint Design: Start call center guide; Thorough review FE build; FE: Finish build
Sprint 46 (4/21 - 5/4) | PM: Hold go/no-go for QA; Request QA for the following sprint; Finish call center guide; submit for call center review; Complete release plan Design: Finish contact center guide; attend QA go/no-go FE: Attend QA go/no-go | PM: Hold go/no-go for QA; Request QA for this sprint; Finish call center guide; submit for call center review Design: Finish contact center guide; attend QA go/no-go FE: Attend QA go/no-go QA: Conduct QA | PM: Finish call center guide; submit for call center review; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Finish contact center guide; attend QA go/no-go; Accessibility tests for staging review FE: Attend QA go/no-go; Accessibility tests for staging review; Techinical docs for privacy and security review; Begin QA fixes QA: Conduct QA
Sprint 47 (5/5 - 5/18) | PM: Meet with analytics team; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Accessibility tests for staging review; UAT research plan; UAT convo guide FE: Accessibility tests for staging review; Techinical docs for privacy and security review QA: Conduct QA | PM: Meet with analytics team; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Accessibility tests for staging review; UAT research plan; UAT convo guide FE: Accessibility tests for staging review; Techinical docs for privacy and security review QA: QA fixes | PM: Hold staging review; Meet with comms; Submit privacy and security ticket; UAT go/no-go Design: Attend UAT go/no-go; UAT recruiting FE: QA fixes; Staging review fixes
Sprint 48 (5/19 - 6/1) | PM: Hold staging review; Meet with comms; Submit privacy and security ticket Design: FE: QA fixes | PM: Hold staging review; Meet with comms; Submit privacy and security ticket; UAT go/no-go Design: Attend UAT go/no-go; UAT recruiting FE: QA fixes, if still needed; Staging review fixes | PM: Design: Conduct UAT FE: UAT fixes
Sprint 49 (6/2 - 6/15) | PM: UAT go/no-go Design: Attend UAT go/no-go; UAT recruiting FE: QA fixes, if still needed; Staging review fixes | PM: Design: Conduct UAT FE: UAT fixes | PM: Launch go/no go; Monitor launch to 25% Design: N/A FE: Launch to 25%
Sprint 50 (6/16 - 6/29) | PM: Design: Conduct UAT FE: UAT fixes | PM: Launch go/no go; Monitor launch to 25% Design: N/A FE: Launch to 25% | PM: Monitor launch to 50%, 100% Design: N/A FE: Launch to 50%; 100%
Sprint 51 (6/30 - 7/13) | PM: Launch go/no go; Monitor launch to 25% Design: N/A FE: Launch to 25% | PM: Monitor launch to 50%, 100% Design: N/A FE: Launch to 50%; 100% | Continued monitoring of analytics Submit for full accessibility review
Sprint 52 (7/14 - 7/27) | PM: Monitor launch to 50%, 100% Design: N/A FE: Launch to 50%; 100% | Continued monitoring of analytics Submit for full accessibility review | Post-launch checkin with VSP
Sprint 53 (7/28 - 8/10) | Continued monitoring of analytics Submit for full accessibility review | Post-launch checkin with VSP
Sprint 54 (8/11 - 8/24) | Post-launch checkin with VSP

## Comms_Notification prefs
Communications permissions/notification preferences: Long term planning
Sprints | Planned tasks | Notes
Sprint 44 (3/24 - 4/6) | Design/Backend integration PM: Schedule and hold design intent collab; Meet with Terry to better understand timeline so we can scope/plan Design: Continue design; Attend design intent collab BE: Finish build
Sprint 45 (4/7 - 4/20) | Design/backend integration PM: IA review with VSP; Internal long-term planning Design: IA review; Work with content on all content that is *not* coming from VA Profile FE: Technical discovery BE: Finish build if extra time needed
Sprint 46 (4/21 - 5/4) | Frontend build PM: Samara to do KPI planning FE: Start build | We'll need to know what the groups are in case we need special filters like filtering out health care notifications for people who don't have VA health care
Sprint 47 (5/5 - 5/18) | Frontend build/research prep PM: Submit ticket for analytics review (VSP); Start putting together midpont review request (don't submit); Work with Liz on preliminary list of test cases/users for QA (can be rough draft) Design: Start on research plan/finish research plan if we have real content/data from VA Profile; Work with AJ on preliminary list of test cases/users for QA (can be rough draft) FE: Continue or finish build
Sprint 48 (5/19 - 6/1) | Frontend build/research prep FE: If not already done, finish build
We can't plan past this point because we don't know when VA Profile will have final content/data. We need this in order to finish the research convo guide, to conduct usability testing, and to move on to QA and the rest of the pre-launch checklist.
Sprint 49 (6/2 - 6/15)
Sprint 50 (6/16 - 6/29)
Sprint 51 (6/30 - 7/13)
Sprint 52 (7/14 - 7/27)
Sprint 53 (7/28 - 8/10)
Sprint 54 (8/11 - 8/24)
General project tasks
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings
Additional notes
Things to consider for this project/planning: - After meeting with Terry and coming up with internal plan, we should regroup with FE to discuss. - Should we do InVision testing? This seems pointless if we don't have real data. We may want to start frontend build and wait until we have real content in live code to do usability testing (and then QA and the rest of the VSP checks). - How are we going to handle staging users? — We'll need to know exactly what notifications need to go out so we can find users that will see those.

## Preferred med facility
Preferred medical facility
Sprints | Planned tasks
Sprint 44 (3/24 - 4/6) | PM: Schedule and hold design intent collab; Meet with VAOS to better understand timeline so we can scope/plan; Internal long term planning Design: Finish design; Attend design intent collab
Sprint 45 (4/7 - 4/20) | PM: IA review with VSP Design: Content?; IA review
Sprint 46 (4/21 - 5/4) | VAOS works on design PM: Work with Liz on list of test cases/test users for the profile; Samara to talk to Lauren about KPI planning Design: Work with AJ on list of test cases/test users for the profile; Collaborate with Peter as needed on design; Start on research plan (though we won't be able to finish until next sprint)
Sprint 47 (5/5 - 5/18) | VAOS & Auth exp collaborate on research PM: Coordinate on ticketing and to-dos with Lauren Ernest; Submit ticket for analytics review (VSP); Prep for Midpoint review Design: Work with Peter to put together research plan; Work with Peter to put together convo guide; Work with Peter to put together prototype
Sprint 48 (5/19 - 6/1) | Kickoff recruiting/start research PM: Coordinate on ticketing and to-dos with Lauren Ernest; Hold Midpint review Design: Kickoff recruiting; start research
Sprint 49 (6/2 - 6/15) | Build PM: Coordinate on ticketing and to-dos with Lauren Ernest; Design: Finish research; Write up findings; modify designs FE: Begin build
Sprint 50 (6/16 - 6/29) | Build PM: Coordinate on ticketing and to-dos with Lauren Ernest; Finalize list of test cases with Liz/VAOS; Get test cases into Test Rail Design: Finalize list of test cases with AJ/VAOS; Get test cases into Test Rail; Review build FE: Continue or finish build
Sprint 51 (6/30 - 7/13) | Finish build PM: Coordinate on ticketing and to-dos with Lauren Ernest; Request QA for next sprint; hold QA go/no-go Design: Review build FE: Finish build if not already done
Sprint 52 (7/14 - 7/27) | QA/Start completing pre-launch checklist items
Sprint 53 (7/28 - 8/10) | Pre-launch checklist items
Sprint 54 (8/11 - 8/24) | Pre-launch checklist items
Sprint 55 (8/25 - 9/7) | UAT
Sprint 56 (9/8 - 9/21) | Launch?
Sprint 57 (9/22 - 10/5)
General project tasks
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Techinical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings

## Direct deposit for edu
Direct deposit: Long term planning
Sprints | Planned tasks
Sprint 44 (3/24 - 4/6) | PM: Hold go/no-go FE: Wrap updated content in a react widget so it will show conditionally throughout phased launch #21725 (needs to be done as early in the sprint as possible before go/no-go); Launch to 10%
Sprint 45 (4/7 - 4/20) | PM: Monitor launches to 25% and 50%; Samara to keep eBenefits and BGS updated on launch; Let content team know anticipated 100% date so that they can publish the updated content page. #20096 FE: Launch to 25% and 50%
Sprint 46 (4/21 - 5/4) | PM: Monitor launch to 100%; Samara to confirm retirement date with eBenefits FE: Launch to 100%
Sprint 47 (5/5 - 5/18) | Continued monitoring of analytics Submit for full accessibility review
Sprint 48 (5/19 - 6/1) | Post-launch checkin with VSP

## Task list for projects
General project tasks
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings