## My VA
My VA redesign: Long term planning
Sprints | Estimate #1: Conservative estimate (though assumes no roadblocks) | Estimate #2: Accelerated timeline | Actual plan
Sprint 44 (3/24 - 4/6) | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build
Sprint 45 (4/7 - 4/20) | PM: Assist with call center guide; Thorough review of FE build Design: Start call center guide; Thorough review FE build; FE: Finish build | PM: Assist with call center guide; Thorough review of FE build Design: Start call center guide; Thorough review FE build; FE: Finish build | PM: Assist with call center guide; Thorough review of FE build; Submit analytics request Design: Start call center guide; Thorough review FE build; FE: Finish build
Sprint 46 (4/21 - 5/4) | PM: Hold go/no-go for QA; Request QA for the following sprint; Finish call center guide; submit for call center review; Complete release plan Design: Finish contact center guide; attend QA go/no-go FE: Final tickets; Attend QA go/no-go | PM: Hold go/no-go for QA; Request QA for this sprint; Finish call center guide; submit for call center review Design: Finish contact center guide; attend QA go/no-go FE: Final tickets; Attend QA go/no-go QA: Conduct QA | PM: Hold go/no-go for QA; Request QA for this sprint; Finish call center guide; submit for call center review Design: Finish contact center guide; attend QA go/no-go FE: Final tickets; Attend QA go/no-go
Sprint 47 (5/5 - 5/18) | PM: Meet with analytics team; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Accessibility tests for staging review; UAT research plan; UAT convo guide; Mini-usability study FE: Accessibility tests for staging review; Technical docs for privacy and security review QA: Conduct QA | PM: Meet with analytics team; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Accessibility tests for staging review; UAT research plan; UAT convo guide FE: Accessibility tests for staging review; Techinical docs for privacy and security review QA: QA fixes | PM: Meet with analytics team if needed/available; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Accessibility tests for staging review; UAT research plan if not already done; UAT convo guide if not already done; post-launch planning, if time FE: Accessibility tests for staging review; Technical docs for privacy and security review; If time/needed, start on QA fixes QA: Conduct QA
Sprint 48 (5/19 - 6/1) | PM: Hold staging review; Submit privacy and security ticket; Meet with comms (Leslie Byford); Hold UAT go/no-go if dependencies allow Design: No tasks for redesign work. - Action items work: Discovery: how can we better elevate action items?; Begin exploration of elevating action items FE: QA fixes | PM: Hold staging review; Meet with comms; Submit privacy and security ticket; UAT go/no-go Design: Attend UAT go/no-go; UAT recruiting FE: QA fixes, if still needed; Staging review fixes | PM: Hold staging review; Submit privacy and security ticket; Meet with comms (Leslie Byford); Hold UAT go/no-go if dependencies allow Design: No tasks for redesign work. - Action items work: Discovery: how can we better elevate action items?; Begin exploration of elevating action items FE: QA fixes
Sprint 49 (6/2 - 6/15) | PM: UAT go/no-go Design: Tressa out 6/10 - 6/17 Attend UAT go/no-go; UAT recruiting** Don't schedule sessions until Tressa is back from leave - Action items work: Work on explorations; Finish them if time; discuss with team if time FE: QA fixes, if still needed; Staging review fixes | PM: Design: Conduct UAT FE: UAT fixes
Sprint 50 (6/16 - 6/29) | PM: Design: Tressa's out until 6/17 Conduct UAT - Action items work: If explorations weren't finished in previous sprint, finish those and discuss with team; Determine method for testing FE: UAT fixes | PM: Launch go/no go; Monitor launch to 25% Design: [Start post-launch research planning] FE: Launch to 25%
Sprint 51 (6/30 - 7/13) | PM: Launch go/no go; Monitor launch to 25% Design: - Action items work: Plan for and recruit for research Conduct research if not done; if done, write up research and share recommendations FE: Launch to 25% | PM: Monitor launch to 50%, 100% Design: [Post-launch research planning] FE: Launch to 50%; 100%
Sprint 52 (7/14 - 7/27) | PM: Monitor launch to 50%, 100% Design: - Action items work: Conduct research; Summarize research FE: Launch to 50%; 100% | Continued monitoring of analytics Submit for full accessibility review Run post-launch testing/research
Sprint 53 (7/28 - 8/10) | Continued monitoring of analytics Submit for full accessibility review Run post-launch testing/research | Post-launch checkin with VSP
Sprint 54 (8/11 - 8/24) | Post-launch checkin with VSP

## Comms_Notification prefs
Communications permissions/notification preferences: Long term planning
Sprints | Planned tasks | Notes
Sprint 44 (3/24 - 4/6) | Design/Backend integration PM: Schedule and hold design intent collab; Meet with Terry to better understand timeline so we can scope/plan Design: Continue design; Attend design intent collab BE: Finish build
Sprint 45 (4/7 - 4/20) | Design/backend integration PM: IA review with VSP Design: IA review; Work with content on all content that is *not* coming from VA Profile; Design documentation for frontend BE: Finish build if extra time needed
Sprint 46 (4/21 - 5/4) | Start tech discovery PM: Samara to do KPI planning; Check in with VA Profile on progress; Work with VANotify and VEText to refine list of notifications Design: Work with content and IA to refine list of notifications FE: Technical discovery | We'll need to know what the groups are in case we need special filters like filtering out health care notifications for people who don't have VA health care
Sprint 47 (5/5 - 5/18) | Has frontend tech discovery happened? Design: Content review and finalize items and groups; Share these with VANotify and VEText for concurrence; Share back to VA Profile team; IA review FE: Tech discovery if it didn't happen; Break down tickets
Sprint 48 (5/19 - 6/1) | Frontend build/Research prep if time PM: Check in with VA Profile on progress; Put test cases together; Prep for midpoint review Design: Work with AJ to put together test cases; Research plan and convo guide if time FE: Start build
Sprint 49 (6/2 - 6/15) | Frontend build PM: Hold midpoint review Design: Recruit for research; Start research if time FE: Continue or finish build
Sprint 50 (6/16 - 6/29) | Frontend build/Conduct research & summarize PM: Design: Run/finish research; Summarize research; If time, update designs and frontend documentation as necessary FE: If not already done, finish build and implement changes from research
Sprint 51 (6/30 - 7/13) | ON HOLD BASED ON VANOTIFY'S INTEGRATION ESTIMATE Design: If needed, update designs and frontend documentation FE: If needed, implement updates from research
Sprint 52 (7/14 - 7/27) | ON HOLD BASED ON VANOTIFY'S INTEGRATION ESTIMATE
Sprint 53 (7/28 - 8/10) | ON HOLD BASED ON VANOTIFY'S INTEGRATION ESTIMATE
Sprint 54 (8/11 - 8/24) | ON HOLD BASED ON VANOTIFY'S INTEGRATION ESTIMATE PM: Request QA for sprint 56 Design: Complete call center guide updates --> You can update the existing profile call center guide and just add a section to it for notification preferences
Sprint 55 (8/25 - 9/7) | QA go/no-go PM: QA go/no-go; Submit ticket for analytics review; Submit for contact center review Design: N/A FE: Attend QA go/no-go BE: Attend QA go/no-go
Sprint 56 (9/8 - 9/21) | QA PM: Start prep for staging and privacy reviews Design: UAT planning; Accessibility tests for staging review QA: Hold QA and create tickets FE: Fixes from QA; Accessibiility tests for staging review
Sprint 58 (9/22 - 10/5) | PM: Hold Staging and privacy reviews; UAT go/no-go Design: Recruit for UAT
Sprint 59 (10/6 - 10/19) | PM: Launch go/no-go Design: Hold UAT FE: Fixes from UAT
Sprint 60 (10/20 - 11/2) | PM: Monitor launch to 25%/50% FE: Flip switch to 25%/50%
Sprint 61 (11/3- 11/16) | PM: Monitor launch to 100% FE: Flip switch to 100%
Sprint 62 (11/17 - 11/30) | Full 508 accessibility review
Sprint 63 (12/1 - 12/14)
Sprint 64 (12/15 - 12/28)
Additional notes
Things to consider for this project/planning: - After meeting with Terry and coming up with internal plan, we should regroup with FE to discuss. - Should we do InVision testing? This seems pointless if we don't have real data. We may want to start frontend build and wait until we have real content in live code to do usability testing (and then QA and the rest of the VSP checks). - How are we going to handle staging users? — We'll need to know exactly what notifications need to go out so we can find users that will see those.

## Preferred med facility
Preferred medical facility
Sprints | Planned tasks
Sprint 44 (3/24 - 4/6) | PM: Schedule and hold design intent collab; Meet with VAOS to better understand timeline so we can scope/plan; Internal long term planning Design: Finish design; Attend design intent collab
Sprint 45 (4/7 - 4/20) | PM: IA review with VSP Design: Content?; IA review; Design documentation for frontend
Sprint 46 (4/21 - 5/4) | VAOS works on design PM: Work with Liz on list of test cases/test users for the profile; Future planning with VAOS; Samara to talk to Lauren about KPI planning Design: Work with AJ on list of test cases/test users for the profile; Collaborate with Peter as needed on design; Start on research plan (though we won't be able to finish until next sprint)
Sprint 47 (5/5 - 5/18) | VAOS finishes design; Auth exp mini study PM: Coordinate on ticketing and to-dos with Lauren Ernest; Meet with VAOS as needed Design: Work with Peter to make sure design *and copy* is finished; Liz to run mini study; IA review for this work; Collab with Peter on convo guide
Sprint 48 (5/19 - 6/1) | VAOS & Auth exp recruit and run research PM: Coordinate on ticketing and to-dos with Lauren Ernest; Prep for Midpoint review Design: Work with Peter to recruit and run research; Update FE documentation if there were copy changes as a result of review with content and IA FE: Technical discovery; Break down tickets for build
Sprint 49 (6/2 - 6/15) | VAOS & Auth exp summarize research; FE starts build PM: Coordinate on ticketing and to-dos with Lauren Ernest; Hold Midpoint review? Design: Work with Peter on research summary; Update designs as needed; Update FE documentation as needed FE: Start build
Sprint 50 (6/16 - 6/29) | Continue or finish build PM: Continued coordination with VAOS team; Finalize test cases; Submit ticket for analytics review (VSP); Request QA for Sprint 52 Design: Finalize test cases FE: Continue or finish build
Sprint 51 (6/30 - 7/13) | Finish build if not already done ** Note on QA**: It might help to have our QA around the same time as the VAOS QA simply so that doesn't hold up our/their progress moving towards launch. But this is optional and you should coordinate with Lauren on this. PM: QA go/no-go; Submit for contact center review Design: Update profile documentation for contact center guide FE: Finish build if not already done; Attend QA go/no-go BE: Attend QA go/no-go
Sprint 52 (7/14 - 7/27) | QA PM: Coordinate on release plan with Lauren Ernest; Prep for staging review; Prep for privacy review Design: Work with Peter on UAT research plan and convo guide; Accessibility tests for staging review FE: Fixes from QA; Accessibility tests for staging review QA: Conduct QA and create tickets as needed
Sprint 53 (7/28 - 8/10) | Hold staging & privacy review PM: Hold staging & privacy review; Coordinate UAT go/no-go with Lauren Ernest; Hold UAT go/no-go Design: Attend UAT go/no-go; Recruit for UAT FE: Attend UAT go/no-go
Sprint 54 (8/11 - 8/24) | UAT PM: Coordinate Launch go/no-go with Lauren Ernest; Hold launch go/no-go Design: Hold UAT FE: UAT fixes
Sprint 55 (8/25 - 9/7) | Begin launch PM: Coordinate launch with VAOS; Monitor phased launch FE: Flip switch to 25%; Flip switch to 50%
Sprint 56 (9/8 - 9/21) | Complete launch PM: Coordinate launch with VAOS; Monitor phased launch FE: Flip switch to 100%
Sprint 57 (9/22 - 10/5) | Submit for full 508 accessibility audit

## Additional research
Preferred medical facility
Sprints | Planned tasks
Sprint 48 (5/19 - 6/1) | N/A
Sprint 49 (6/2 - 6/15) | N/A
Sprint 50 (6/16 - 6/29) | Liz's research project:Refine the plan we've started, start grabbing screenshots #24973
Sprint 51 (6/30 - 7/13) | Dependent's user roles research: Planning and recruiting - Not sure yet whether this will be Liz or Tressa. Figure out who should work on this based on bandwidth and other project work. Liz's research project: Wrap up screenshots, do any supplemental reading needed to answer questions, start synthesis #24974 - If Liz needs to do the dependent's user roles research, we will have to move the general auth experience research back by a couple of sprints
Sprint 52 (7/14 - 7/27) | Dependent's user roles research: Conduct research and summarize findings - Not sure yet whether this will be Liz or Tressa. Figure out who should work on this based on bandwidth and other project work. Liz's research project: Complete synthesis + present to team #24977 - If Liz needs to do the dependent's user roles research, we will have to move the general auth experience research back by a couple of sprints
Sprint 53 (7/28 - 8/10)
Sprint 54 (8/11 - 8/24)
Sprint 55 (8/25 - 9/7)
Sprint 56 (9/8 - 9/21)
Sprint 57 (9/22 - 10/5)

## Long term resourcing by person
| Sprint 48 (5/19 - 6/1) | Sprint 49 (6/2 - 6/15) | Sprint 50 (6/16 - 6/29) | Sprint 51 (6/30 - 7/13) | Sprint 52 (7/14 - 7/27) | Sprint 53 (7/28 - 8/10) | Sprint 54 (8/11 - 8/24) | Sprint 55 (8/25 - 9/7) | Sprint 56 (9/8 - 9/21) | Sprint 57 (9/22 - 10/5)
| Q2 2021 |  |  | Q3 2021 | [5 empty] | Q3/Q4/2021
Tressa Furner
My VA | 70% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0%
Dependents user roles research** If Tressa does this work. Other work may need to move around accordingly. | 0% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0%
Liz Lantz
Notification preferences | 30% | 40% | 40% | 30% | 30% | 10% | 30% | 0% | 0% | 0%
Preferred facility | 40% | 40% | 10% | 20% | 30% | 10% | 30% | 0% | 0% | 0%
Auth exp. research project | 0% | 0% | 20% | 20% | 20% | 0% | 0% | 0% | 0% | 0%
General profile updates | 15% | 15% | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Dependents user roles research** If Liz does this work. Other work may need to move around accordingly. | 0% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0%
Erik Hansen
My VA | 20% | 20% | 20% | 10% | 10% | 0% | 0% | 0% | 0% | 0%
Notification preferences | 40% | 40% | 40% | 20% | 20% | 0% | 20% | 10% | 10% | 0%
Preferred facility | 20% | 40% | 40% | 20% | 20% | 10% | 20% | 10% | 10% | 0%
General profile updates | 5% | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Taylor Mitchell
General profile updates | 10% | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Lihan Li
Notification preferences | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0%
Preferred facility | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0%
User roles & permissions | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD

## Task list for projects
General project tasks
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings