## My VA
My VA
Sprints | Payment info updates | Medical copays
Sprint 58 (10/6 - 10/19) | Meet with edu team | N/A
Sprint 59 (10/20 - 11/2) | Scope project PM: Schedule discussion on discovery findings for end of sprint Design: Discovery -- determine the direction of work | N/A
Sprint 60 (11/3- 11/16) | Determine next steps PM: Nothing Design: Present findings; work with team to determine next steps; FE: Technical discovery, if needed | N/A
Sprint 61 (11/17 - 11/30) | Project pivot to payment information PM: Collab kickoff Design: Additional payment info discovery; Meet with debt team to understand feature; preliminary designs; Define scope FE: Do we need any technical discovery now? I don't think so. | N/A
Sprint 62 (12/1 - 12/14) | Design intent - Design; Design intent - Technical discovery | N/A
Sprint 63 (12/15 - 12/28) | Research/midpoint review planning - Midpoint review planning, including starting to put together list of test cases - Finish design if not already done - Technical discovery | N/A
Sprint 64 (12/29 - 1/11) | Midpoint review; Research planning - Hold midpoint review - Research planning/convo guide/ recruit; If not done, finish design on how to handle "benefits you might be interested in"; if done, create FE tickets - Prototype build on payment info | N/A
Sprint 65 (1/12 - 1/25) | Continue build - Conduct and summarize research - Update documentation if time - Updates from user research (may go into the following sprint depending on updates) - Determine what, if anything, still needs to happen with FE build, and complete build | N/A
Sprint 66 (1/26 - 2/8) | Finish build - PM: Do we need UAT? - Design for any updates coming out of testing; Onboard Angela - Request QA depending where build is at -- Are we ready for QA? - Update documentation if needed - Finish build | N/A
Sprint 67 (2/9 - 2/22) | Liz to transition My VA work over to Angela; All final updates ahead of QA - PM: Review QA test cases and make sure they are accurate given any updates from user testing - Team does informal click through of the feature to make sure it is ready for QA - Design: Contact center guide; maybe My VA sketch file clean up - FE: Error states; user testing updates | Medical copays - PM/Design: Have planning discussion
Sprint 68 (2/23 - 3/8) | QA - PM: Analytics request (Look at what we set for KPIs to give Heather details on what she should include in this request; add yo exisiting My VA dashboard) - QA (doesn't need to be day 1 of the sprint) - UAT planning | Medical copays PM: Fill out collab kickoff ticket, but clarify we likely won't need more than a design review and maybe research review Design: Discovery; design exploration
Sprint 69 (3/9 - 3/22) | Updates from QA | Medical copays PM: ? Design: Research planning and prep -- are we doing a "mock" A/B test? Getting feedback during payment UAT? Both?
Sprint 70 (3/23 - 4/5) | Pre-launch prep | Research?
Sprint 71 (4/6 - 4/19) | Pre-launch prep; UAT | Research?
Sprint 72 (4/20 - 5/3) | Launch to 25% & 50% | QA if needed; Analytics request; Pre-launch reviews
Sprint 73 (5/4 - 5/17) | Launch to 100% | Pre-launch reviews
Sprint 74 (5/18 - 5/31) |  | Launch

## Alerts
On-site notifications MVP
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | PM: Meet with VANotify Design: Finalize MVP design; meet with VANotify; meet with IA; finalize MVP notification list. FE: Support as needed. BE: Talk to platform; Technical diagram;
Sprint 59 (10/20 - 11/2) | Kickoff collab cycle; start build PM: Collab cycle kickoff; Collab cycle design intent; meet with VANotify Design: Design intent; content; meet with VANotify FE: Meet with VANotify BE: Start build ; meet with VANotify
Sprint 60 (11/3- 11/16) | Finalize designs, if possible; Determine next steps and timeline for VANotify; Continue build PM: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates Design: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates; Finalize designs, if not already done; Work with content, if not already done FE: Work with team to define requirements for VANotify updates; Support team as necessary BE: Work with team to define requirements for VANotify updates; Continue build
Sprint 61 (11/17 - 11/30) | Revisit this work - Talk to Chris and make sure that pivoting is OK - Redefine MVP (elevate all appointments, messages, debt?; Maybe just elevate appointments?) - PM: Given this pivot, do we need to redo any of the collab cycle? - Tressa: Mockup/explorations
Sprint 62 (12/1 - 12/14) | Project on hold
Sprint 63 (12/15 - 12/28) | Resume project - Define needs for VANotify, determine what they need to do, and determine timeline for any work they need to do. - Figure out what design needs to be updated; Update design; determine if we need additional user testing or not based on updates; follow-up with collab cycle design intent issues/tickets and let them know about our pivot. - Determine next steps for backend build; If possible, Tom can start to implement build if possible | Research - Midpoint review - Finish design if not already done - Research planning/convo guide - Start FE build? Finish backend build.
Sprint 64 (12/29 - 1/11) | Start build - PM: Determine VANotify's timeline based on availability; Determine QA/testing strategy -- talk to Leah/Denise/Maria about this; Midpoint review prep (note: testing for this is going to happen as part of payment info testing) - Design: Research prep is happening as part of payment info - FE: Start FE build if possible - BE: Lihan to meet with VANotify to determine how the backend should receive data from VANotify; Start build | Research - Conduc research/summarize research if needed - Continue/finish FE build - QA prep
Sprint 65 (1/12 - 1/25) | Hold midpoint review - PM: Midpoint review - Design: Research (as part of payment info work) - FE: Is there anything that still needs to happen? - BE: Build -- how many sprints? -- Is VANotify going away again because of contract issues? | Finish build - Contact center guides - Finish build
Sprint 66 (1/26 - 2/8) | Continue BE build as necessary Are we on hold until VANotify can work on this?
Sprint 67 (2/9 - 2/22) | On hold until VANotify is available
Sprint 68 (2/23 - 3/8) | On hold until VANotify is available
Sprint 69 (3/9 - 3/22) | On hold until VANotify is available
Sprint 70 (3/23 - 4/5) | QA
Sprint 71 (4/6 - 4/19) | Pre-launch prep
Sprint 72 (4/20 - 5/3) | Pre-launch prep
Launch to 25% & 50%
Launch to 100%

## Profile_LGBTQ data
Personal information updates (LGBTQ data)
Sprints | Planned tasks | Notes
Sprint 58 (10/6 - 10/19) | Team onboards - Meet with team - Collab cycle kickoff - Collab cycle design intent - Create tickets for design, content, and frontend - Get relevant data points (ie What is populating dropdown menus?) - Complete initial mockups
Sprint 59 (10/20 - 11/2) | Continue design and FE build PM: Collab cycle IA review; Create frontend documentation as designs are finalized Design: Meet with content and update designs accordingly FE: Continue frontend build
Sprint 60 (11/3- 11/16) | PM: Continue to work behind the scenes to collab with MPI to get work ready for backend development Design: Transition call with Kevin; Update designs, if needed; Usability research plan FE: Continue build BE: Sit in on MPI calls
Sprint 61 (11/17 - 11/30) | PM: Start putting together list of test cases; Prep for midpoint review Design: Usability research plan & convo guide FE: Continue build (how much longer is this going to take?) BE: Start backend integration if MPI is ready
Sprint 62 (12/1 - 12/14) | Midpoint review, Recruit for user testing, Start testing (?) continue FE build; BE build (tickets TBD after we talk to this team on Wednesday) | Unclear when we'll be able to start backend build
Sprint 63 (12/15 - 12/28) | Recruit for testing if possible - Recruit for testing if contract is back - Continue whatever is left of the frontend build
Sprint 64 (12/29 - 1/11) | Research - PM: ? - Design: Conduct research; Synthesize test results - FE: Continue FE Build - BE: Start BE build
Sprint 65 (1/12 - 1/25) | Finish research; determine next steps with build based on VA Profile's direction - Summarize research - Any FE tasks? - Start BE build if possible
Sprint 66 (1/26 - 2/8) | Design: Changes from research FE: Work on changes from research, if changes are mocked up before the end of the sprint BE: Still on hold
Sprint 67 (2/9 - 2/22) | PM: When will we be ready for QA? Design: Finish all design updates FE: Implement design updates BE: Start BE build if possible; VA Profile is targeting 2/14 for being ready for us
Sprint 68 (2/23 - 3/8) | Finish BE build; Contact center guide
Sprint 69 (3/9 - 3/22) | QA; UAT planning
Sprint 70 (3/23 - 4/5) | Pre-launch prep
Sprint 71 (4/6 - 4/19) | Pre-launch prep/UAT
Sprint 72 (4/20 - 5/3) | Launch to 25% & 50%
Sprint 73 (5/4 - 5/17) | Launch to 100%

## Profile_Bad address
Bad address indicator
Sprints | Planned tasks | Notes
Sprint 65 (1/12 - 1/25) | PM/PO prediscovery; BE to review swagger docs
Sprint 66 (1/26 - 2/8) | Continue PM discovery; product outline
Sprint 67 (2/9 - 2/22) | Collab cycle kickoff; If time allows with personal info work, start design brainstorming
Sprint 68 (2/23 - 3/8) | Design, design intent
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)
Sprint 71 (4/6 - 4/19)
Sprint 72 (4/20 - 5/3)
Sprint 73 (5/4 - 5/17)

## Profile_Military service info
Military service info
Sprints | Planned tasks | Notes
Sprint 66 (1/26 - 2/8) | Samara does discovery; Submits intake form; Maybe initial convos with VA Profile
Sprint 67 (2/9 - 2/22) | Still waiting to hear back from VA Profile
Sprint 68 (2/23 - 3/8) | Project planning; Collab cycle kickoff; product outline
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)
Sprint 71 (4/6 - 4/19)
Sprint 72 (4/20 - 5/3)
Sprint 73 (5/4 - 5/17)

## MHV_VA.gov profile research
MHV/VA.gov Profile research
Sprints | Planned tasks | Notes
Sprint 65 (1/12 - 1/25) | Talk to Lauren/Tracey/Meg
Sprint 66 (1/26 - 2/8) | Samara: Outline rough research plan; If it seems like research can happen soon, get Chris on board.
Sprint 67 (2/9 - 2/22) | Chris to talk to MHV and make intros
Sprint 68 (2/23 - 3/8) | Liz to start research planning (if Liz isn't needing to do UAT planning for payments)
Sprint 69 (3/9 - 3/22) | Research
Sprint 70 (3/23 - 4/5) | Research
Sprint 71 (4/6 - 4/19) | Research
Sprint 72 (4/20 - 5/3) | Liz to deliver final report

## LT project planning
Long term planning until end of contract
Project | Sprint 67 (2/9 - 2/22) | Sprint 68 (2/23 - 3/8) | Sprint 69 (3/9 - 3/22) | Sprint 70 (3/23 - 4/5) | Sprint 71 (4/6 - 4/19) | Sprint 72 (4/20 - 5/3) | Sprint 73 (5/4 - 5/17)
My VA
Payment updates | Finish design/FE build | QA | Updates from QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
Single on-site notification MVP (Debt notification) | On hold | TBD | TBD | TBD | TBD | TBD | TBD
Profile
Personal information updates | Start BE build | Finish BE build | QA | Updates from QA | Pre-launch | Launch 25 - 50% | Launch 100%
Bad address indicator | Design discovery | Design | TBD | TBD | TBD | TBD | TBD

## Planning by person
Planning by person
Sprints | Tressa | Liz | Christina | Taylor | Adam | Lihan | Tom
Sprint 63 (12/15 - 12/28) | My VA payments work; On-site alerts updates, if applicable | Start transition to take over My VA work; out most of sprint but needs something | Research recruiting; out most of the sprint; needs more work | View Payments technical discovery | Personal information updates | Out; then hopefully can start on MPI work if possible; otherwise, on hold with all work | Onboarding; Can we start him on the VANotify integration? Andre should assign him to help another team
Sprint 64 (12/29 - 1/11) | Tressa's last sprint; Research planning for payment info | Personal info research; continue taking over My VA from Tressa; Finish "benefits you might be interested in updates" if not done | Personal info research | View payments build; On-site notifications MVP build; Benefits you might be interested in update | Personal information updates | Resolve direct deposit issues; On-site notifications build | Resolve direct deposit issues; Personal info build
Sprint 65 (1/12 - 1/25) | Rolling off team | Payment history/on-site notifications research | Personal info research summary; likely needs more work | Likely needs more work | Likely needs more work | Start on on-site notifications build, if possible | Start on personal info build, if possible
Sprint 66 (1/26 - 2/8)
Sprint 67 (2/9 - 2/22)
Sprint 68 (2/23 - 3/8)
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings