## My VA_Payment history
My VA
Sprints | Payment info updates
Sprint 58 (10/6 - 10/19) | Meet with edu team
Sprint 59 (10/20 - 11/2) | Scope project PM: Schedule discussion on discovery findings for end of sprint Design: Discovery -- determine the direction of work
Sprint 60 (11/3- 11/16) | Determine next steps PM: Nothing Design: Present findings; work with team to determine next steps; FE: Technical discovery, if needed
Sprint 61 (11/17 - 11/30) | Project pivot to payment information PM: Collab kickoff Design: Additional payment info discovery; Meet with debt team to understand feature; preliminary designs; Define scope FE: Do we need any technical discovery now? I don't think so.
Sprint 62 (12/1 - 12/14) | Design intent - Design; Design intent - Technical discovery
Sprint 63 (12/15 - 12/28) | Research/midpoint review planning - Midpoint review planning, including starting to put together list of test cases - Finish design if not already done - Technical discovery
Sprint 64 (12/29 - 1/11) | Midpoint review; Research planning - Hold midpoint review - Research planning/convo guide/ recruit; If not done, finish design on how to handle "benefits you might be interested in"; if done, create FE tickets - Prototype build on payment info
Sprint 65 (1/12 - 1/25) | Continue build - Conduct and summarize research - Update documentation if time - Updates from user research (may go into the following sprint depending on updates) - Determine what, if anything, still needs to happen with FE build, and complete build
Sprint 66 (1/26 - 2/8) | Finish build - PM: Do we need UAT? - Design for any updates coming out of testing; Onboard Angela - Request QA depending where build is at -- Are we ready for QA? - Update documentation if needed - Finish build
Sprint 67 (2/9 - 2/22) | Liz to transition My VA work over to Angela; All final updates ahead of QA - PM: Review QA test cases and make sure they are accurate given any updates from user testing - Team does informal click through of the feature to make sure it is ready for QA - Design: Contact center guide; maybe My VA sketch file clean up - FE: Error states; user testing updates
Sprint 68 (2/23 - 3/8) | QA - PM: Analytics request (Look at what we set for KPIs to give Heather details on what she should include in this request; add yo exisiting My VA dashboard) - QA (doesn't need to be day 1 of the sprint) - UAT planning
Sprint 69 (3/9 - 3/22) | PRE LAUNCH!! This assumes call center guide is all done. - PM: Make sure analytics updates get implemented; Put together launch plan; Prep for staging review; Hold staging review if we don't need to do any significant updates from QA (can be towards the end of the sprint if necessary) - Design: Updates from QA, if applicable - FE: Updates from QA if applicable; Prep for privacy and security review - BE: Prepare any technical diagrams or other documentation needed for the privacy and security review
Sprint 70 (3/23 - 4/5) | Because of BGS delays… - QA updates - Finish prep and hold staging review - Privacy and security review - UAT go/no-go - Start recruiting for UAT?
Sprint 71 (4/6 - 4/19) | Pre-launch prep - Updates from the staging review, if necessary - If we are good to go, recruit and hold UAT - PM: During UAT, make sure we can see analytics come in - Privacy and security review (ticket open and pending review)
Sprint 72 (4/20 - 5/3) | PM Monitor launch to 25% Monitor launch to 50% For V2 updates: Collab cycle kickoff For V2 updates: Collab cycle design intent FE Flip feature flag for launch to 25% Flip feature flag for launch to 50% Design For V2 updates: Collab cycle design intent For V2 updates: Updates coming out of design intent
Sprint 73 (5/4 - 5/17) | Launch to 100%
Sprint 74 (5/18 - 5/31) | Observe stats after launch
Sprint 75 (6/1 - 6/14) | Submit for 508 review
Sprint 76 (6/15 - 6/28)
Sprint 77 (6/29 - 7/12)
Sprint 78 (7/13 - 7/26)
Sprint 79 (7/27 - 8/9)
Sprint 80 (8/10 - 8/23)
Sprint 81 (8/24 - 9/6)
Sprint 82 (9/7 - 9/20)

## My VA_Alerts
On-site notifications MVP
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | PM: Meet with VANotify Design: Finalize MVP design; meet with VANotify; meet with IA; finalize MVP notification list. FE: Support as needed. BE: Talk to platform; Technical diagram;
Sprint 59 (10/20 - 11/2) | Kickoff collab cycle; start build PM: Collab cycle kickoff; Collab cycle design intent; meet with VANotify Design: Design intent; content; meet with VANotify FE: Meet with VANotify BE: Start build ; meet with VANotify
Sprint 60 (11/3- 11/16) | Finalize designs, if possible; Determine next steps and timeline for VANotify; Continue build PM: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates Design: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates; Finalize designs, if not already done; Work with content, if not already done FE: Work with team to define requirements for VANotify updates; Support team as necessary BE: Work with team to define requirements for VANotify updates; Continue build
Sprint 61 (11/17 - 11/30) | Revisit this work - Talk to Chris and make sure that pivoting is OK - Redefine MVP (elevate all appointments, messages, debt?; Maybe just elevate appointments?) - PM: Given this pivot, do we need to redo any of the collab cycle? - Tressa: Mockup/explorations
Sprint 62 (12/1 - 12/14) | Project on hold
Sprint 63 (12/15 - 12/28) | Resume project - Define needs for VANotify, determine what they need to do, and determine timeline for any work they need to do. - Figure out what design needs to be updated; Update design; determine if we need additional user testing or not based on updates; follow-up with collab cycle design intent issues/tickets and let them know about our pivot. - Determine next steps for backend build; If possible, Tom can start to implement build if possible | Research - Midpoint review - Finish design if not already done - Research planning/convo guide - Start FE build? Finish backend build.
Sprint 64 (12/29 - 1/11) | Start build - PM: Determine VANotify's timeline based on availability; Determine QA/testing strategy -- talk to Leah/Denise/Maria about this; Midpoint review prep (note: testing for this is going to happen as part of payment info testing) - Design: Research prep is happening as part of payment info - FE: Start FE build if possible - BE: Lihan to meet with VANotify to determine how the backend should receive data from VANotify; Start build | Research - Conduc research/summarize research if needed - Continue/finish FE build - QA prep
Sprint 65 (1/12 - 1/25) | Hold midpoint review - PM: Midpoint review - Design: Research (as part of payment info work) - FE: Is there anything that still needs to happen? - BE: Build -- how many sprints? -- Is VANotify going away again because of contract issues? | Finish build - Contact center guides - Finish build
Sprint 66 (1/26 - 2/8) | Continue BE build as necessary Are we on hold until VANotify can work on this?
Sprint 67 (2/9 - 2/22) | On hold until VANotify is available
Sprint 68 (2/23 - 3/8) | On hold until VANotify is available
Sprint 69 (3/9 - 3/22) | 3/15: Intro work to the new VANotify team PM: Regroup with VANotify on this work and determine what next steps are for them; determine timelines for VANotify and FE work FE: Connect FE to backend API Lihan created
Sprint 70 (3/23 - 4/5) | VANotify to start work; evaluate what they need to do so we can plan our own timelines; Do we have a plan for QA?
Sprint 71 (4/6 - 4/19) | Determine next steps for VANotify; Determine next steps for Tom
Sprint 72 (4/20 - 5/3) | ???
Sprint 73 (5/4 - 5/17) | Determine continued backend needs so we can plan for Tom accordingly;
Sprint 74 (5/17 - 5/31) | QA; Analytics request; Call center guide (can use My VA guide)
Pre-launch prep
Pre-launch prep
Launch to 25% & 50%
Launch to 100%

## My VA_Audit
My VA: Audit
Sprints | Planned tasks
Sprint 69 (3/9 - 3/22) | Research review; Discuss next steps
Sprint 70 (3/23 - 4/5) | Design: - Audit nametag - Audit claims & appeals - Exploration for showing amount in debts & copays section/not showing debt and copay info as a notification style.
Sprint 71 (4/6 - 4/19) | Design: - Audit health care - Audit benefit payments and debts - Audit applications in progress - If time, regroup with Samara/AJ (or Heather if she is still here) on existing states
Sprint 72 (4/20 - 5/3) | On hold due to other work
Sprint 73 (5/4 - 5/17) | Design: - Review audit with team (to make sure nothing is missing - Start streamlining states for each section - Start with nametag and payment info (since we are working on it anyway) - Each section should always appear on the page - Each section should have the following: loadin state; blank state(s); content state(s); error state(s). Note: the nametag might be a little different, as there's never a totally blank state, and we don't show big error alerts for content we can't load.
Sprint 74 (5/17 - 5/31) | Design: - Continue simplifying each section - Claims & appeals - Health care
Sprint 75 (6/1 - 6/14) | Collab kickoff; Design intent
Sprint 76 (6/15 - 6/28) | Design updates; Research plan
Sprint 77 (6/29 - 7/12) | Research
Sprint 78 (7/13 - 7/26) | Research updates | NOTE: Consider smaller, iterative launches
Sprint 79 (7/27 - 8/9) | DOCUMENTATION SPRINT
Sprint 80 (8/10 - 8/23) | FE build
Sprint 81 (8/24 - 9/6) | FE build
Sprint 82 (9/7 - 9/20) | FE build
QA
Pre-launch
Pre-launch
Launch

## Profile_LGBTQ data
Personal information updates (LGBTQ data)
Sprints | Planned tasks | Notes
Sprint 58 (10/6 - 10/19) | Team onboards - Meet with team - Collab cycle kickoff - Collab cycle design intent - Create tickets for design, content, and frontend - Get relevant data points (ie What is populating dropdown menus?) - Complete initial mockups
Sprint 59 (10/20 - 11/2) | Continue design and FE build PM: Collab cycle IA review; Create frontend documentation as designs are finalized Design: Meet with content and update designs accordingly FE: Continue frontend build
Sprint 60 (11/3- 11/16) | PM: Continue to work behind the scenes to collab with MPI to get work ready for backend development Design: Transition call with Kevin; Update designs, if needed; Usability research plan FE: Continue build BE: Sit in on MPI calls
Sprint 61 (11/17 - 11/30) | PM: Start putting together list of test cases; Prep for midpoint review Design: Usability research plan & convo guide FE: Continue build (how much longer is this going to take?) BE: Start backend integration if MPI is ready
Sprint 62 (12/1 - 12/14) | Midpoint review, Recruit for user testing, Start testing (?) continue FE build; BE build (tickets TBD after we talk to this team on Wednesday) | Unclear when we'll be able to start backend build
Sprint 63 (12/15 - 12/28) | Recruit for testing if possible - Recruit for testing if contract is back - Continue whatever is left of the frontend build
Sprint 64 (12/29 - 1/11) | Research - PM: ? - Design: Conduct research; Synthesize test results - FE: Continue FE Build - BE: Start BE build
Sprint 65 (1/12 - 1/25) | Finish research; determine next steps with build based on VA Profile's direction - Summarize research - Any FE tasks? - Start BE build if possible
Sprint 66 (1/26 - 2/8) | Design: Changes from research FE: Work on changes from research, if changes are mocked up before the end of the sprint BE: Still on hold
Sprint 67 (2/9 - 2/22) | PM: When will we be ready for QA? Design: Finish all design updates FE: Implement design updates BE: Start BE build if possible; VA Profile is targeting 2/14 for being ready for us
Sprint 68 (2/23 - 3/8) | Continue build; Finish design; Finish FE PM: If content isn't done, assess when we think that will be done based on Danielle's availability; If time, work on contact center guide Design: Finish all design updates; If time, work on contact center guide FE: Finish FE if possible BE: Provide estimate of how long BE build will take; Continue BE build
Sprint 69 (3/9 - 3/22) | Design: Finish design if it's not done; If done, contact center guide FE: Finish any updates if they are not already done; If done, project is on pause for Adam until backend is ready to connect to frontend BE: Continue BE (Tom out 3/10, 11, 14)
Sprint 70 (3/23 - 4/5) | Continue BE PM: Call center guide; Determine when we can do QA based on new BE timeline Design: Change gender identity BACK to single select; Create a couple mockups showing preferred name/gender identity without the other fields; Call center guide FE: Change gender identity BACK to single select; Implement final design updates; Gate separating preferred name/gender identity from pronouns/sexual orientation; Hide pronouns/sexual orientation on the frontend as part of the gate BE: Continue BE integration; Determine how our approach changes given separate launch of pronouns and sexual orientation
Sprint 71 (4/6 - 4/19) | Finish BE - PM: Request QA for 5/4 - 5/17 sprint; Finish all QA prep; Finish call center guide - Design: Finish call center guide; UAT planning if time - FE: Start connecting frontent to backend; Finish this if possible - BE: Finish BE
Sprint 72 (4/20 - 5/3) | Anything outstanding from last sprint, plus... PM: Submit call center guide for review Design: Complete UAT planning FE: Connect FE to BE if that still needs to happen Everyone: Once the feature is fully complete in staging, everyone on the project should go into staging and review the feature to make sure it's ready for QA
Sprint 73 (5/4 - 5/17) | QA PM: Figure out what pages need to be updated re: profile URLs and work with the right folks to get that updated; QA go/no-go; Analytics request; Launch plan QA: QA
Sprint 74 (5/18 - 5/31) | Pre-launch prep; Staging review; privacy review; UAT recruiting
Sprint 75 (6/1 - 6/14) | UAT
Sprint 76 (6/15 - 6/28) | Launch to 25% & 50%
Sprint 77 (6/29 - 7/12) | Launch to 100%
Sprint 78 (7/13 - 7/26)
Sprint 79 (7/27 - 8/9)
Sprint 80 (8/10 - 8/23)
Sprint 81 (8/24 - 9/6)
Sprint 82 (9/7 - 9/20)

## Profile_Bad address
Bad address indicator
Sprints | Planned tasks | Notes
Sprint 65 (1/12 - 1/25) | PM/PO prediscovery; BE to review swagger docs
Sprint 66 (1/26 - 2/8) | Continue PM discovery; product outline
Sprint 67 (2/9 - 2/22) | Collab cycle kickoff; If time allows with personal info work, start design brainstorming
Sprint 68 (2/23 - 3/8) | Design: Tickets for design in profile and email
Sprint 69 (3/9 - 3/22) | Design intent PM: Intro work to VANotify; determine what they need to do, if anything. Probably something given that we want to send an initial email blast and then emails for users when the bad address indicator gets added. Design: Design if not done the previous sprint; Design intent; Work with content on profile/email copy; start FE documentation on when the alert shows in the profile and when the email will be sent out (initial blast; whenever a new bad address is added)
Sprint 70 (3/23 - 4/5) | PM: Start on QA use cases (this will not be completed yet); Figure out how we can get a staging user with the bad address indicator for testing (might require working with VA Profile) Design: Design intent if it didn't happen; Finalize designs; FE documentation
Sprint 71 (4/6 - 4/19) | On Hold (Sharon onboarding; Team focused on other work)
Sprint 72 (4/20 - 5/3) | PM and Design on hold BE: BE work on email blast/individual emails
Sprint 73 (5/4 - 5/17) | PM: Start on QA use cases (this will not be completed yet) Figure out how we can get a staging user with the bad address indicator for testing (might require working with VA Profile) Design: Create high fidelity mockups
Sprint 74 (5/18 - 5/31) | PM: Midpoint review prep Design: Put together research plan; Put together convo guide FE: Assuming Design work is done for profile, start FE build if time (personal info work takes priority)
Sprint 75 (6/1 - 6/14) | PM: Hold midpoint review Design: Recruit for research
Sprint 76 (6/15 - 6/28) | PM: QA Prep Design: Conduct research; Summarize research
Sprint 77 (6/29 - 7/12) | PM: Request QA Design: Updates from research FE: Updates from research, if applicable BE: Updates from research, if applicable
Sprint 78 (7/13 - 7/26) | QA PM: Analytics request; Launch planning Design: Contact center guide QA: Hold QA
Sprint 79 (7/27 - 8/9) | UAT prep and planning; Updates from QA if applicable; Prep for staging & privacy reviews
Sprint 80 (8/10 - 8/23) | Staging review; Privacy review; UAT recruiting
Sprint 81 (8/24 - 9/6) | UAT
Sprint 82 (9/7 - 9/20) | Launch to 25% & 50%
Launch to 100%; DOCUMENTATION SPRINT
Once this work is done, take 2 sprints to create master doc of contact info

## MHV_VA.gov profile research
MHV/VA.gov Profile research
Sprints | Planned tasks | Notes
Sprint 65 (1/12 - 1/25) | Talk to Lauren/Tracey/Meg
Sprint 66 (1/26 - 2/8) | Samara: Outline rough research plan; If it seems like research can happen soon, get Chris on board.
Sprint 67 (2/9 - 2/22) | Chris to talk to MHV and make intros
Sprint 68 (2/23 - 3/8) | Liz to start research planning (if Liz isn't needing to do UAT planning for payments) --> this is only per availability, and note that we haven't been intro'd to MHV yet (but hopefully will soon)
Sprint 69 (3/9 - 3/22) | Conduct all stakeholder interviews (MHV + VA.gov)
Sprint 70 (3/23 - 4/5) | User research prep & recruiting; User interviews
Sprint 71 (4/6 - 4/19) | Liz to compile final report
Sprint 72 (4/20 - 5/3) | Share final report with team
Sprint 73 (5/4 - 5/17) | Samara to do planning on next steps
Sprint 74 (5/18 - 5/31)

## Profile_Military service info
Military service info
Sprints | Planned tasks | Notes
Sprint 70 (3/23 - 4/5) | Samara to prep product outline
Sprint 71 (4/6 - 4/19) | N/A
Sprint 72 (4/20 - 5/3)
Sprint 73 (5/4 - 5/17) | Have Tom start this work; Collab kickoff; Begin backend integration
Sprint 74 (5/18 - 5/31) | Sharon to prep QA test cases; Analytics planning
Sprint 75 (6/1 - 6/14) | Finish backend; request QA
Sprint 76 (6/15 - 6/28) | QA; Prep for staging review
Sprint 77 (6/29 - 7/12) | Staging review; Privacy & security review
Sprint 78 (7/13 - 7/26) | Launch to 25%; Launch to 50%
Sprint 79 (7/27 - 8/9) | Launch to 100%
Sprint 80 (8/10 - 8/23)
Sprint 81 (8/24 - 9/6)
Sprint 82 (9/7 - 9/20)
Once this work is done, take 1 sprint to create master doc of Military info

## Profile_Notification Preference
Notification preferences updates
Sprints | Planned tasks | Notes
Add comp & pen payment notification: Start date TBD; Originally mentioned in VA Profile meeting on 3/10
Sprint 69 (3/9 - 3/22) | VA Profile let us know about new comp & pen payment notification
Sprint 70 (3/23 - 4/5) | Get update on comp & pen notification and do planning; Update prescriptions notification to accommodate additional facilities
Sprint 71 (4/6 - 4/19) | Get Christina to update mocks with the new claims deposit notification info, then get feedback from IA and content
Sprint 72 (4/20 - 5/3)
Sprint 73 (5/4 - 5/17)
Sprint 74 (5/18 - 5/31)
Once this work is done, take 1 sprint to create master doc of notification prefs functionality

## Profile_Direct deposit
Direct deposit improvements
Sprints | Planned tasks | Notes
Sprint 68 (2/23 - 3/8) | Samara: Try to figure out what error codes mean so we can look into them
Sprint 69 (3/9 - 3/22) | N/A -- Waiting for availability
Sprint 70 (3/23 - 4/5) | N/A -- Waiting for availability
Sprint 71 (4/6 - 4/19) | N/A -- Waiting for availability
Sprint 72 (4/20 - 5/3) | N/A -- Waiting for availability
Sprint 73 (5/4 - 5/17) | Design: Update direct deposit mockups in Sketch (apparently outdated); Mock up screens to for direct deposit being persistently available; Clarify edu feedback that if they receive checks, they need to call to start direct deposit
Sprint 74 (5/18 - 5/31) | FE: Implement always showing direct deposit
Sprint 75 (6/1 - 6/14) | PM: Observe analytics
Sprint 76 (6/15 - 6/28) | PM: Observe analytic
Sprint 77 (6/29 - 7/12) | PM: Get Jason to send us Medallia data; Assess how direct deposit feedback has changed. Are people saying they should see DD info that are not seeing it? Determine next steps.
Once this work is done, take 1- 2 sprints to create master doc of direct deposit functionality

## Profile_Update documentation
Profile: Create better documentation
Sprints | Planned tasks | Notes
Sprint 72 (4/20 - 5/3) | N/A
Sprint 73 (5/4 - 5/17) | N/A
Sprint 74 (5/18 - 5/31) | Planning: Figure out structure for documentation
Sprint 75 (6/1 - 6/14) | Document Personal Info
Sprint 76 (6/15 - 6/28) | Document Contact Info
Sprint 77 (6/29 - 7/12) | Document Military Info
Sprint 78 (7/13 - 7/26) | Document Direct Deposit
Sprint 79 (7/27 - 8/9) | Document Notification Preferences
Sprint 80 (8/10 - 8/23) | Document Account Settings
Sprint 81 (8/24 - 9/6) | Document Connected Apps
Sprint 82 (9/7 - 9/20)

## LT project planning
Long term planning until end of contract
Project | Sprint 67 (2/9 - 2/22) | Sprint 68 (2/23 - 3/8) | Sprint 69 (3/9 - 3/22) | Sprint 70 (3/23 - 4/5) | Sprint 71 (4/6 - 4/19) | Sprint 72 (4/20 - 5/3) | Sprint 73 (5/4 - 5/17)
My VA
Payment updates | Finish design/FE build | QA | Updates from QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
Single on-site notification MVP (Debt notification) | On hold | TBD | TBD | TBD | TBD | TBD | TBD
Profile
Personal information updates | Start BE build | Finish BE build | QA | Updates from QA | Pre-launch | Launch 25 - 50% | Launch 100%
Bad address indicator | Design discovery | Design | TBD | TBD | TBD | TBD | TBD

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings