## My VA
My VA: Payment info updates
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | Meet with edu team
Sprint 59 (10/20 - 11/2) | Scope project PM: Schedule discussion on discovery findings for end of sprint Design: Discovery -- determine the direction of work
Sprint 60 (11/3- 11/16) | Determine next steps PM: Nothing Design: Present findings; work with team to determine next steps; FE: Technical discovery, if needed
Sprint 61 (11/17 - 11/30) | Project pivot to payment information PM: Collab kickoff Design: Additional payment info discovery; Meet with debt team to understand feature; preliminary designs; Define scope FE: Do we need any technical discovery now? I don't think so.
Sprint 62 (12/1 - 12/14) | Design intent - Design; Design intent - Technical discovery
Sprint 63 (12/15 - 12/28) | Research/midpoint review planning - Midpoint review planning, including starting to put together list of test cases - Finish design if not already done - Technical discovery | Also have Tressa do some explorations around better elevating action items
Sprint 64 (12/29 - 1/11) | Midpoint review; Research planning - Hold midpoint review - Research planning/convo guide/ recruit; If not done, finish design on how to handle "benefits you might be interested in"; if done, create FE tickets - Prototype build on payment info
Sprint 65 (1/12 - 1/25) | Continue build - Request QA depending where build is at - Conduct and summarize research - Update documentation if time - Updates from user research (may go into the following sprint depending on updates) - Determine what, if anything, still needs to happen with FE build, and complete build
Sprint 66 (1/26 - 2/8) | Finish build - QA prep (maybe QA?) - Contact center guide; Update documentation if needed - Finish build
Sprint 67 (2/9 - 2/22) | QA - QA - Updates from QA
Sprint 68 (2/23 - 3/8) | Pre-launch prep
Sprint 69 (3/9 - 3/22) | Pre-launch prep
Sprint 70 (3/23 - 4/5) | Launch to 25% & 50%
Launch to 100%

## Alerts
On-site notifications MVP
Sprints | Planned tasks
Sprint 58 (10/6 - 10/19) | PM: Meet with VANotify Design: Finalize MVP design; meet with VANotify; meet with IA; finalize MVP notification list. FE: Support as needed. BE: Talk to platform; Technical diagram;
Sprint 59 (10/20 - 11/2) | Kickoff collab cycle; start build PM: Collab cycle kickoff; Collab cycle design intent; meet with VANotify Design: Design intent; content; meet with VANotify FE: Meet with VANotify BE: Start build ; meet with VANotify
Sprint 60 (11/3- 11/16) | Finalize designs, if possible; Determine next steps and timeline for VANotify; Continue build PM: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates Design: Collab cycle design intent (if it didn't happen last sprint); Work with team to define requirements for VANotify updates; Finalize designs, if not already done; Work with content, if not already done FE: Work with team to define requirements for VANotify updates; Support team as necessary BE: Work with team to define requirements for VANotify updates; Continue build
Sprint 61 (11/17 - 11/30) | Revisit this work - Talk to Chris and make sure that pivoting is OK - Redefine MVP (elevate all appointments, messages, debt?; Maybe just elevate appointments?) - PM: Given this pivot, do we need to redo any of the collab cycle? - Tressa: Mockup/explorations
Sprint 62 (12/1 - 12/14) | Project on hold
Sprint 63 (12/15 - 12/28) | Resume project - Define needs for VANotify, determine what they need to do, and determine timeline for any work they need to do. - Figure out what design needs to be updated; Update design; determine if we need additional user testing or not based on updates; follow-up with collab cycle design intent issues/tickets and let them know about our pivot. - Determine next steps for backend build; If possible, Tom can start to implement build if possible | Research - Midpoint review - Finish design if not already done - Research planning/convo guide - Start FE build? Finish backend build.
Sprint 64 (12/29 - 1/11) | Start build - PM: Determine VANotify's timeline based on availability; Determine QA/testing strategy -- talk to Leah/Denise/Maria about this; Midpoint review prep (note: testing for this is going to happen as part of payment info testing) - Design: Research prep is happening as part of payment info - FE: Start FE build if possible - BE: Lihan to meet with VANotify to determine how the backend should receive data from VANotify; Start build | Research - Conduc research/summarize research if needed - Continue/finish FE build - QA prep
Sprint 65 (1/12 - 1/25) | Hold midpoint review - PM: Midpoint review - Design: Research (as part of payment info work) - FE: Is there anything that still needs to happen? - BE: Build -- how many sprints? | Finish build - Contact center guides - Finish build
Sprint 66 (1/26 - 2/8) |  | QA
Sprint 67 (2/9 - 2/22) |  | Pre-launch prep
Sprint 68 (2/23 - 3/8) |  | Pre-launch prep
Sprint 69 (3/9 - 3/22) |  | Launch to 25% & 50%
Sprint 70 (3/23 - 4/5) |  | Launch to 100%

## Comms_Notification prefs
Communications permissions/notification preferences
Sprints | Planned tasks | Notes
Sprint 62 (12/1 - 12/14) | Full 508 accessibility review
Sprint 63 (12/15 - 12/28) | Full 508 accessibility review
Sprint 64 (12/29 - 1/11)
Sprint 65 (1/12 - 1/25)
Sprint 66 (1/26 - 2/8)
Sprint 67 (2/9 - 2/22)
Sprint 68 (2/23 - 3/8)
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)
Additional notes
Things to consider for this project/planning: - After meeting with Terry and coming up with internal plan, we should regroup with FE to discuss. - Should we do InVision testing? This seems pointless if we don't have real data. We may want to start frontend build and wait until we have real content in live code to do usability testing (and then QA and the rest of the VSP checks). - How are we going to handle staging users? — We'll need to know exactly what notifications need to go out so we can find users that will see those.

## Profile_LGBTQ data
Personal information updates (LGBTQ data)
Sprints | Planned tasks | Notes
Sprint 58 (10/6 - 10/19) | Team onboards - Meet with team - Collab cycle kickoff - Collab cycle design intent - Create tickets for design, content, and frontend - Get relevant data points (ie What is populating dropdown menus?) - Complete initial mockups
Sprint 59 (10/20 - 11/2) | Continue design and FE build PM: Collab cycle IA review; Create frontend documentation as designs are finalized Design: Meet with content and update designs accordingly FE: Continue frontend build
Sprint 60 (11/3- 11/16) | PM: Continue to work behind the scenes to collab with MPI to get work ready for backend development Design: Transition call with Kevin; Update designs, if needed; Usability research plan FE: Continue build BE: Sit in on MPI calls
Sprint 61 (11/17 - 11/30) | PM: Start putting together list of test cases; Prep for midpoint review Design: Usability research plan & convo guide FE: Continue build (how much longer is this going to take?) BE: Start backend integration if MPI is ready
Sprint 62 (12/1 - 12/14) | Midpoint review, Recruit for user testing, Start testing (?) continue FE build; BE build (tickets TBD after we talk to this team on Wednesday) | Unclear when we'll be able to start backend build
Sprint 63 (12/15 - 12/28) | Recruit for testing if possible - Recruit for testing if contract is back - Continue whatever is left of the frontend build
Sprint 64 (12/29 - 1/11) | Research - PM: ? - Design: Conduct research; Synthesize test results - FE: Continue FE Build - BE: Start BE build
Sprint 65 (1/12 - 1/25) | Finish research; determine next steps with build based on VA Profile's direction - Summarize research - Any FE tasks? - Start BE build if possible
Sprint 66 (1/26 - 2/8) | Finish BE build
Sprint 67 (2/9 - 2/22) | QA
Sprint 68 (2/23 - 3/8) | Pre-launch prep
Sprint 69 (3/9 - 3/22) | Pre-launch prep
Sprint 70 (3/23 - 4/5) | Launch to 25% & 50%
Launch to 100%
Additional notes

## LT project planning
Long term planning until end of contract
Project | Sprint 61 (11/17 - 11/30) | Sprint 62 (12/1 - 12/14) | Sprint 63 (12/15 - 12/28) | Sprint 64 (12/29 - 1/11) | Sprint 65 (1/12 - 1/25) | Sprint 66 (1/26 - 2/8) | Sprint 67 (2/9 - 2/22) | Sprint 68 (2/23 - 3/8) | Sprint 69 (3/9 - 3/22) | Sprint 70 (3/23 - 4/5) | Sprint 71 (4/6 - 4/19) | Sprint 72 (4/20 - 5/3)
My VA
Payment updates | Discovery | Design | Design/Research prep/Build | Research/Build | Finish build | QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
User roles & permissions research | Synthesis & read-out
Single on-site notification MVP (Debt notification) | Samara to do background research | Re-define project/Design/BE Build | Resume project: complete design | Build | Build | Build | Finish build | QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
Unauth homepage updates |  |  |  |  | TBD | TBD | TBD | TBD | TBD | TBD
Profile
Personal information updates | Research prep/FE build | Research/FE build/Start BE build | BE/FE build | BE/FE build | Finish build/QA | Pre-launch | Pre-launch | Launch 25 - 50% | Launch 100%
Notification preferences | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD

## Planning by person
Planning by person
Sprints | Tressa | Liz | Christina | Taylor | Adam | Lihan | Tom
Sprint 63 (12/15 - 12/28) | My VA payments work; On-site alerts updates, if applicable | Start transition to take over My VA work; out most of sprint but needs something | Research recruiting; out most of the sprint; needs more work | View Payments technical discovery | Personal information updates | Out; then hopefully can start on MPI work if possible; otherwise, on hold with all work | Onboarding; Can we start him on the VANotify integration? Andre should assign him to help another team
Sprint 64 (12/29 - 1/11) | Tressa's last sprint; Research planning for payment info | Personal info research; continue taking over My VA from Tressa; Finish "benefits you might be interested in updates" if not done | Personal info research | View payments build; On-site notifications MVP build; Benefits you might be interested in update | Personal information updates | Resolve direct deposit issues; On-site notifications build | Resolve direct deposit issues; Personal info build
Sprint 65 (1/12 - 1/25) | Rolling off team | Payment history/on-site notifications research | Personal info research summary; likely needs more work | Likely needs more work | Likely needs more work | Start on on-site notifications build, if possible | Start on personal info build, if possible
Sprint 66 (1/26 - 2/8)
Sprint 67 (2/9 - 2/22)
Sprint 68 (2/23 - 3/8)
Sprint 69 (3/9 - 3/22)
Sprint 70 (3/23 - 4/5)

## Task list for projects
General project tasks (updated April 2021)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Technical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings