## My VA redesign
My VA redesign: Long term planning
Sprints | Estimate #1: Conservative estimate (though assumes no roadblocks) | Estimate #2: Accelerated timeline | Estimate #3: Super aggressive timeline
Sprint 44 (3/24 - 4/6) | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build | PM: Design: Finish design; Update My VA test cases; Talk to Trevor about assistive tech review FE: Continue build
Sprint 45 (4/7 - 4/20) | PM: Assist with call center guide; Thorough review of FE build Design: Start call center guide; Thorough review FE build; FE: Finish build | PM: Assist with call center guide; Thorough review of FE build Design: Start call center guide; Thorough review FE build; FE: Finish build | PM: Assist with call center guide; Thorough review of FE build; Meet with analytics team; Hold go/no-go for QA; Request QA for next sprint Design: Start call center guide; Thorough review FE build; FE: Finish build
Sprint 46 (4/21 - 5/4) | PM: Hold go/no-go for QA; Request QA for the following sprint; Finish call center guide; submit for call center review; Complete release plan Design: Finish contact center guide; attend QA go/no-go FE: Attend QA go/no-go | PM: Hold go/no-go for QA; Request QA for this sprint; Finish call center guide; submit for call center review Design: Finish contact center guide; attend QA go/no-go FE: Attend QA go/no-go QA: Conduct QA | PM: Finish call center guide; submit for call center review; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Finish contact center guide; attend QA go/no-go; Accessibility tests for staging review FE: Attend QA go/no-go; Accessibility tests for staging review; Techinical docs for privacy and security review; Begin QA fixes QA: Conduct QA
Sprint 47 (5/5 - 5/18) | PM: Meet with analytics team; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Accessibility tests for staging review; UAT research plan; UAT convo guide FE: Accessibility tests for staging review; Techinical docs for privacy and security review QA: Conduct QA | PM: Meet with analytics team; begin filling out ticket for staging review; begin filling out ticket for privacy review Design: Accessibility tests for staging review; UAT research plan; UAT convo guide FE: Accessibility tests for staging review; Techinical docs for privacy and security review QA: QA fixes | PM: Hold staging review; Meet with comms; Submit privacy and security ticket; UAT go/no-go Design: Attend UAT go/no-go; UAT recruiting FE: QA fixes; Staging review fixes
Sprint 48 (5/19 - 6/1) | PM: Hold staging review; Meet with comms; Submit privacy and security ticket Design: FE: QA fixes | PM: Hold staging review; Meet with comms; Submit privacy and security ticket; UAT go/no-go Design: Attend UAT go/no-go; UAT recruiting FE: QA fixes, if still needed; Staging review fixes | PM: Design: Conduct UAT FE: UAT fixes
Sprint 49 (6/2 - 6/15) | PM: UAT go/no-go Design: Attend UAT go/no-go; UAT recruiting FE: QA fixes, if still needed; Staging review fixes | PM: Design: Conduct UAT FE: UAT fixes | PM: Launch go/no go; Monitor launch to 25% Design: N/A FE: Launch to 25%
Sprint 50 (6/16 - 6/29) | PM: Design: Conduct UAT FE: UAT fixes | PM: Launch go/no go; Monitor launch to 25% Design: N/A FE: Launch to 25% | PM: Monitor launch to 50%, 100% Design: N/A FE: Launch to 50%; 100%
Sprint 51 (6/30 - 7/13) | PM: Launch go/no go; Monitor launch to 25% Design: N/A FE: Launch to 25% | PM: Monitor launch to 50%, 100% Design: N/A FE: Launch to 50%; 100% | Continued monitoring of analytics Submit for full accessibility review
Sprint 52 (7/14 - 7/27) | PM: Monitor launch to 50%, 100% Design: N/A FE: Launch to 50%; 100% | Continued monitoring of analytics Submit for full accessibility review | Post-launch checkin with VSP
Sprint 53 (7/28 - 8/10) | Continued monitoring of analytics Submit for full accessibility review | Post-launch checkin with VSP
Sprint 54 (8/11 - 8/24) | Post-launch checkin with VSP

## Comms perm_Notification prefs
Communications permissions/notification preferences: Long term planning
Sprints | Planned tasks
Sprint 44 (3/24 - 4/6) | PM: Schedule and hold design intent collab; Meet with Terry to better understand timeline so we can scope/plan Design: Finish design; Attend design intent collab BE: Finish build
Sprint 45 (4/7 - 4/20) | PM: IA review with VSP; Internal long-term planning Design: IA review
Sprint 46 (4/21 - 5/4)
Sprint 47 (5/5 - 5/18)
Sprint 48 (5/19 - 6/1)
Tasks that still need to happen (not already in above plan)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Final design updates after review with Terry/Design team/Auth exp team | Technical discovery, if needed | QA fixes | Research Plan Review
Attend all meetings that require the PM | Work with content to get finalized | Frontend build | Staging review fixes | Analytics Request
Work with team on ticket creation | Research plan | QA fixes | Attend any required reviews | Midpoint Review
Plan and hold all required VSP reviews | Research convo guide | Accessibility fixes | Technical docs for privacy and security review | QA
Put together list of staging users for QA in tandem with design | Submit for research recruiting | Staging review fixes | Attend all go/no-go meetings | Contact Center Review
Assist with design documentation for frontend | Conduct & summarize research | Attend any required reviews | Attend UAT | Staging Review
Work with analytics to get dashboards created | Design documentation for frontend | Accessibility tests for staging review | UAT fixes | Privacy and Security Review
Assist with call center guide | Put together list of staging users for QA in tandem with PM | Technical docs for privacy and security review |  | Full Accessibility and 508 Office Audit
QA go/no-go meeting | Call center guide | Attend all go/no-go meetings |  | Post-launch Check-in
UAT go/no-go meeting | UAT research plan | Attend UAT
Launch go/no-go meeting | UAT convo guide | UAT fixes
| Submit for UAT recruiting | Flip on switch for phased launches
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings

## Preferred med facility
Preferred medical facility
Sprints | Planned tasks
Sprint 44 (3/24 - 4/6) | PM: Schedule and hold design intent collab; Meet with VAOS to better understand timeline so we can scope/plan Design: Finish design; Attend design intent collab
Sprint 45 (4/7 - 4/20) | PM: IA review with VSP; Internal long-term planning Design: IA review
Sprint 46 (4/21 - 5/4)
Sprint 47 (5/5 - 5/18)
Sprint 48 (5/19 - 6/1)
Tasks that still need to happen (not already in above plan)
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Final design updates after review with VAOS/Design team/Auth exp team | Technical discovery, if needed | QA fixes | Research Plan Review
Attend all meetings that require the PM | Work with content to get finalized | Frontend build | Staging review fixes | Analytics Request
Work with team on ticket creation | Research plan | QA fixes | Attend any required reviews | Midpoint Review
Plan and hold all required VSP reviews | Research convo guide | Accessibility fixes | Technical docs for privacy and security review | QA
Put together list of staging users for QA in tandem with design | Submit for research recruiting | Staging review fixes | Attend all go/no-go meetings | Contact Center Review
Assist with design documentation for frontend | Conduct & summarize research | Attend any required reviews | Attend UAT | Staging Review
Work with analytics to get dashboards created | Design documentation for frontend | Accessibility tests for staging review | UAT fixes | Privacy and Security Review
Assist with call center guide | Put together list of staging users for QA in tandem with PM | Technical docs for privacy and security review |  | Full Accessibility and 508 Office Audit
QA go/no-go meeting | Call center guide | Attend all go/no-go meetings |  | Post-launch Check-in
UAT go/no-go meeting | UAT research plan | Attend UAT
Launch go/no-go meeting | UAT convo guide | UAT fixes
| Submit for UAT recruiting | Flip on switch for phased launches
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings

## Direct deposit for edu
Direct deposit: Long term planning
Sprints | Planned tasks
Sprint 44 (3/24 - 4/6) | PM: Hold go/no-go FE: Wrap updated content in a react widget so it will show conditionally throughout phased launch #21725 (needs to be done as early in the sprint as possible before go/no-go); Launch to 10%
Sprint 45 (4/7 - 4/20) | PM: Monitor launches to 25% and 50%; Samara to keep eBenefits and BGS updated on launch; Let content team know anticipated 100% date so that they can publish the updated content page. #20096 FE: Launch to 25% and 50%
Sprint 46 (4/21 - 5/4) | PM: Monitor launch to 100%; Samara to confirm retirement date with eBenefits FE: Launch to 100%
Sprint 47 (5/5 - 5/18) | Continued monitoring of analytics Submit for full accessibility review
Sprint 48 (5/19 - 6/1) | Post-launch checkin with VSP

## Task list for projects
Project tasks
PM | Design | FE | BE | VSP
General project oversight and expertise throughout the project | Design discovery | Techinical discovery | Technical discovery | Design Intent
Attend all meetings that require the PM | Design | Frontend build | QA fixes | Information Architecture (IA) Request
Work with team on ticket creation | Work with content to get finalized | QA fixes | Staging review fixes | Research Plan Review
Plan and hold all required VSP reviews | Research plan | Accessibility fixes | Attend any required reviews | Analytics Request
Put together list of staging users for QA in tandem with design | Research convo guide | Staging review fixes | Technical docs for privacy and security review | Midpoint Review
Assist with design documentation for frontend | Submit for research recruiting | Attend any required reviews | Attend all go/no-go meetings | QA
Work with analytics to get dashboards created | Conduct & summarize research | Accessibility tests for staging review | Attend UAT | Contact Center Review
Assist with call center guide | Design documentation for frontend | Technical docs for privacy and security review | UAT fixes | Staging Review
QA go/no-go meeting | Put together list of staging users for QA in tandem with PM | Attend all go/no-go meetings |  | Privacy and Security Review
UAT go/no-go meeting | Call center guide | Attend UAT |  | Full Accessibility and 508 Office Audit
Launch go/no-go meeting | UAT research plan | UAT fixes |  | Post-launch Check-in
| UAT convo guide | Flip on switch for phased launches
Submit for UAT recruiting
Conduct UAT & summarize findings
Attend all required VSP reviews
Attend all go/no-go meetings